## Scheduled Segments
block position description | block position id | block position length | block position width | labor team | ship no. | block sequence no. | block no. | block length | block width | block processing time | block output value | planned start time | planned finish time | latest completion time | delay days | advance days | normal advance days
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 757 | 284 | 20 | 18.4 | 72 | 368 | 2018-03-03 | 2018-05-14 | 2018-09-10 | -119 | 0 | 7
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 758 | 294 | 20 | 18.4 | 71 | 368 | 2018-03-03 | 2018-05-13 | 2018-09-08 | -118 | 0 | 7
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 823 | 836 | 6.45 | 21.691 | 53 | 139.9069 | 2018-03-18 | 2018-05-10 | 2018-07-27 | -78 | 0 | 1
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 822 | 826 | 20.852 | 21.691 | 53 | 452.3007 | 2018-03-18 | 2018-05-10 | 2018-07-27 | -78 | 0 | 1
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 810 | 835 | 18 | 17.3 | 40 | 311.4 | 2018-03-26 | 2018-05-05 | 2018-07-27 | -83 | 0 | 9
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1088 | 809 | 825 | 18.455 | 17.3 | 40 | 319.2715 | 2018-03-26 | 2018-05-05 | 2018-07-27 | -83 | 0 | 9
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 803 | 694 | 16.7 | 18.4 | 39 | 307.28 | 2018-03-31 | 2018-05-09 | 2018-07-26 | -78 | 0 | 14
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 802 | 684 | 17.5 | 18.4 | 39 | 322 | 2018-03-31 | 2018-05-09 | 2018-07-26 | -78 | 0 | 14
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 819 | 101 | 30.66 | 9.4 | 61 | 288.204 | 2018-03-25 | 2018-05-25 | 2018-08-11 | -78 | 0 | 7
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 881 | 102 | 16.588 | 12.377 | 39 | 205.3097 | 2018-03-25 | 2018-05-03 | 2018-06-17 | -45 | 0 | 1
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1088 | 856 | 110 | 13 | 5.487 | 42 | 71.331 | 2018-03-25 | 2018-05-06 | 2018-07-03 | -58 | 0 | 0
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1087 | 847 | 272 | 15.89 | 20.773 | 35 | 330.083 | 2018-03-27 | 2018-05-01 | 2018-07-14 | -74 | 0 | 2
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 793 | 182 | 7.9 | 19.9 | 42 | 157.21 | 2018-04-06 | 2018-05-18 | 2018-08-01 | -75 | 0 | 10
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 794 | 192 | 23.8 | 19.9 | 42 | 473.62 | 2018-04-06 | 2018-05-18 | 2018-08-01 | -75 | 0 | 10
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 828 | 683 | 16.6 | 18.9 | 25 | 313.74 | 2018-04-13 | 2018-05-08 | 2018-07-07 | -60 | 0 | 17
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 829 | 693 | 16.6 | 18.9 | 25 | 313.74 | 2018-04-13 | 2018-05-08 | 2018-07-07 | -60 | 0 | 17
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 792 | 154 | 24.839 | 16.385 | 40 | 406.987 | 2018-05-19 | 2018-06-28 | 2018-07-29 | -31 | -29 | 24
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 880 | 101 | 13.007 | 16.37 | 36 | 212.9246 | 2018-04-01 | 2018-05-07 | 2018-06-14 | -38 | 0 | 1
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 867 | 163 | 16.387 | 11.151 | 29 | 182.7314 | 2018-04-08 | 2018-05-07 | 2018-07-03 | -57 | 0 | 7
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1088 | 870 | 173 | 16.387 | 11.151 | 29 | 182.7314 | 2018-04-08 | 2018-05-07 | 2018-07-02 | -56 | 0 | 7
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1088 | 804 | 134 | 19.318 | 18.5 | 45 | 357.383 | 2018-04-13 | 2018-05-28 | 2018-07-30 | -63 | 0 | 12
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 805 | 124 | 16.142 | 18.85 | 45 | 304.2767 | 2018-04-14 | 2018-05-29 | 2018-07-30 | -62 | 0 | 13
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1088 | 869 | 161 | 14.057 | 15.486 | 32 | 217.6867 | 2018-04-03 | 2018-05-05 | 2018-07-05 | -61 | 0 | 1
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 874 | 103 | 24 | 11 | 39 | 264 | 2018-05-26 | 2018-07-04 | 2018-06-30 | 4 | -53 | 1
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1087 | 830 | 143 | 14.606 | 16.186 | 45 | 236.4127 | 2018-04-11 | 2018-05-26 | 2018-07-26 | -61 | 0 | 8
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1087 | 831 | 153 | 19.167 | 16.07 | 45 | 308.0137 | 2018-04-11 | 2018-05-26 | 2018-07-26 | -61 | 0 | 8
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 861 | 122 | 15.531 | 12.2 | 24 | 189.4782 | 2018-04-14 | 2018-05-08 | 2018-07-02 | -55 | 0 | 7
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 848 | 132 | 18.94 | 12.2 | 27 | 231.068 | 2018-04-14 | 2018-05-11 | 2018-07-08 | -58 | 0 | 7
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 862 | 103 | 29.101 | 15.68 | 51 | 456.3037 | 2018-04-15 | 2018-06-05 | 2018-07-29 | -54 | 0 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 787 | 111 | 22.2 | 13.8 | 40 | 306.36 | 2018-06-29 | 2018-08-08 | 2018-07-29 | 10 | -73 | 7
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 857 | 112 | 21 | 5.15 | 26 | 108.15 | 2018-04-11 | 2018-05-07 | 2018-06-15 | -39 | 0 | 0
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 864 | 144 | 15.117 | 16.07 | 24 | 242.9302 | 2018-04-13 | 2018-05-07 | 2018-06-28 | -52 | 0 | 2
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 865 | 154 | 19.39 | 16.07 | 24 | 311.5973 | 2018-04-13 | 2018-05-07 | 2018-06-28 | -52 | 0 | 2
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 797 | 801 | 20.814 | 15.31 | 50 | 318.6623 | 2018-04-16 | 2018-06-05 | 2018-08-06 | -62 | 0 | 5
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 866 | 632 | 13.38 | 17.28 | 15 | 231.2064 | 2018-04-16 | 2018-05-01 | 2018-06-24 | -54 | 0 | 4
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 863 | 622 | 13.38 | 17.28 | 15 | 231.2064 | 2018-04-17 | 2018-05-02 | 2018-06-25 | -54 | 0 | 5
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 879 | 101 | 11.523 | 8.65 | 29 | 99.674 | 2018-04-14 | 2018-05-13 | 2018-06-19 | -37 | 0 | 1
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 871 | 102 | 26.372 | 14.65 | 37 | 386.3498 | 2018-06-06 | 2018-07-13 | 2018-07-05 | 8 | -52 | 1
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 843 | 834 | 26 | 13.72 | 25 | 356.72 | 2018-07-05 | 2018-07-30 | 2018-07-04 | 26 | -76 | 5
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 842 | 824 | 14.342 | 13.72 | 25 | 196.7722 | 2018-04-20 | 2018-05-15 | 2018-07-04 | -50 | 0 | 5
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 760 | 144 | 17.566 | 15.678 | 49 | 275.3997 | 2018-04-22 | 2018-06-10 | 2018-08-24 | -75 | 0 | 7
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 759 | 154 | 19.932 | 15.976 | 51 | 318.4336 | 2018-04-22 | 2018-06-12 | 2018-08-27 | -76 | 0 | 7
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 859 | 835 | 5.59 | 17.008 | 28 | 95.0747 | 2018-04-21 | 2018-05-19 | 2018-07-03 | -45 | 0 | 4
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 858 | 825 | 17.18 | 16.97 | 28 | 291.5446 | 2018-04-21 | 2018-05-19 | 2018-07-03 | -45 | 0 | 4
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1087 | 878 | 832 | 15 | 10.3 | 23 | 154.5 | 2018-04-21 | 2018-05-14 | 2018-06-21 | -38 | 0 | 3
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1087 | 877 | 822 | 12.6 | 10.3 | 23 | 129.78 | 2018-04-21 | 2018-05-14 | 2018-06-21 | -38 | 0 | 3
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 849 | 143 | 13.809 | 15.686 | 22 | 216.608 | 2018-04-23 | 2018-05-15 | 2018-07-01 | -47 | 0 | 5
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 850 | 153 | 18.919 | 15.5 | 22 | 293.2445 | 2018-04-23 | 2018-05-15 | 2018-07-01 | -47 | 0 | 5
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 765 | 124 | 18.618 | 14.354 | 47 | 267.2428 | 2018-04-24 | 2018-06-10 | 2018-08-21 | -72 | 0 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 761 | 134 | 22.828 | 14.354 | 48 | 327.6731 | 2018-07-31 | 2018-09-17 | 2018-08-23 | 25 | -98 | 6
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 795 | 183 | 8.82 | 15.798 | 22 | 139.3384 | 2018-04-23 | 2018-05-15 | 2018-07-14 | -60 | 0 | 4
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 796 | 193 | 15.59 | 15.978 | 22 | 249.097 | 2018-04-23 | 2018-05-15 | 2018-07-14 | -60 | 0 | 4
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1088 | 853 | 835 | 7.416 | 16.884 | 22 | 125.2117 | 2018-04-25 | 2018-05-17 | 2018-06-29 | -43 | 0 | 6
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1088 | 852 | 825 | 19.167 | 16.931 | 22 | 324.5165 | 2018-04-25 | 2018-05-17 | 2018-06-29 | -43 | 0 | 6
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1088 | 873 | 832 | 6.767 | 14.288 | 18 | 96.6869 | 2018-04-25 | 2018-05-13 | 2018-06-23 | -41 | 0 | 5
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 872 | 822 | 16.086 | 14.292 | 18 | 229.9011 | 2018-05-02 | 2018-05-20 | 2018-06-23 | -34 | -7 | 5
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 815 | 283 | 13.7 | 18.32 | 31 | 250.984 | 2018-05-02 | 2018-06-02 | 2018-07-18 | -46 | -5 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 811 | 293 | 22.5 | 18.32 | 31 | 412.2 | 2018-08-09 | 2018-09-09 | 2018-07-19 | 52 | -104 | 7
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1088 | 771 | 628 | 15.6 | 20 | 23 | 312 | 2018-05-03 | 2018-05-26 | 2018-07-25 | -60 | -2 | 7
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1088 | 772 | 638 | 15.6 | 20 | 23 | 312 | 2018-05-01 | 2018-05-24 | 2018-07-25 | -62 | 0 | 7
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1088 | 824 | 631 | 10.53 | 15.97 | 15 | 168.1641 | 2018-05-04 | 2018-05-19 | 2018-07-03 | -45 | -9 | 0
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 812 | 803 | 15.5 | 21 | 30 | 325.5 | 2018-05-08 | 2018-06-07 | 2018-07-12 | -35 | -12 | 1
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 825 | 621 | 8.95 | 15.97 | 15 | 142.9315 | 2018-05-06 | 2018-05-21 | 2018-07-03 | -43 | -9 | 0
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1088 | 789 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2018-05-06 | 2018-05-31 | 2018-07-20 | -50 | -8 | 1
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1088 | 788 | 263 | 16.6 | 18.79 | 25 | 311.914 | 2018-05-06 | 2018-05-31 | 2018-07-20 | -50 | -8 | 1
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1088 | 838 | 623 | 13.38 | 18.79 | 15 | 251.4102 | 2018-05-07 | 2018-05-22 | 2018-06-30 | -39 | -8 | 1
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 839 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2018-05-08 | 2018-05-23 | 2018-06-30 | -38 | -9 | 1
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 844 | 102 | 19.76 | 18.47 | 21 | 364.9672 | 2018-04-29 | 2018-05-20 | 2018-06-27 | -38 | 0 | 0
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 777 | 261 | 20.5 | 18.8 | 34 | 385.4 | 2018-05-08 | 2018-06-11 | 2018-08-01 | -51 | -8 | 0
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 820 | 133 | 21.1 | 18.1 | 29 | 381.91 | 2018-05-11 | 2018-06-09 | 2018-07-10 | -31 | -10 | 1
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 821 | 123 | 20.9 | 18.1 | 29 | 378.29 | 2018-05-08 | 2018-06-06 | 2018-07-10 | -34 | -6 | 1
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 766 | 268 | 10.8 | 20 | 29 | 216 | 2018-05-08 | 2018-06-06 | 2018-08-02 | -57 | -6 | 0
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 776 | 271 | 15.2 | 18.8 | 34 | 285.76 | 2018-05-08 | 2018-06-11 | 2018-08-02 | -52 | -6 | 0
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 840 | 103 | 23.857 | 9.5 | 30 | 226.6415 | 2018-09-10 | 2018-10-10 | 2018-07-07 | 95 | -129 | 2
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 875 | 161 | 13.792 | 9.4 | 18 | 129.6448 | 2018-05-09 | 2018-05-27 | 2018-06-18 | -22 | -6 | 0
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 876 | 171 | 16.655 | 9.4 | 18 | 156.557 | 2018-05-09 | 2018-05-27 | 2018-06-18 | -22 | -6 | 0
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 767 | 278 | 10.8 | 20 | 28 | 216 | 2018-05-09 | 2018-06-06 | 2018-08-01 | -56 | -6 | 0
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 779 | 272 | 14.4 | 17.28 | 31 | 248.832 | 2018-05-10 | 2018-06-10 | 2018-08-02 | -53 | -7 | 0
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 778 | 262 | 14.6 | 17.28 | 31 | 252.288 | 2018-05-10 | 2018-06-10 | 2018-08-02 | -53 | -7 | 0
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 836 | 194 | 18 | 8.3 | 30 | 149.4 | 2018-05-11 | 2018-06-10 | 2018-07-08 | -28 | -7 | 1
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1088 | 841 | 184 | 13.9 | 8.3 | 30 | 115.37 | 2018-05-12 | 2018-06-11 | 2018-07-07 | -26 | -7 | 2
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 783 | 183 | 7.507 | 14.276 | 20 | 107.1699 | 2018-05-14 | 2018-06-03 | 2018-07-17 | -44 | -2 | 6
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 784 | 193 | 14.445 | 14.246 | 20 | 205.7835 | 2018-05-14 | 2018-06-03 | 2018-07-17 | -44 | -2 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 762 | 801 | 28.614 | 19.075 | 34 | 545.812 | 2018-09-18 | 2018-10-22 | 2018-08-06 | 77 | -126 | 9
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 832 | 182 | 23 | 7.3 | 17 | 167.9 | 2018-10-11 | 2018-10-28 | 2018-07-04 | 116 | -153 | 4
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 833 | 192 | 13.889 | 7.3 | 17 | 101.3897 | 2018-05-14 | 2018-05-31 | 2018-07-04 | -34 | -3 | 4
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 816 | 642 | 13.412 | 19.5 | 16 | 261.534 | 2018-05-15 | 2018-05-31 | 2018-07-07 | -37 | -3 | 5
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1087 | 817 | 652 | 13.412 | 19.5 | 16 | 261.534 | 2018-05-12 | 2018-05-28 | 2018-07-07 | -40 | 0 | 5
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1087 | 769 | 124 | 21 | 18.1 | 25 | 380.1 | 2018-05-17 | 2018-06-11 | 2018-07-27 | -46 | 0 | 9
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1087 | 770 | 134 | 21 | 18.1 | 25 | 380.1 | 2018-05-17 | 2018-06-11 | 2018-07-27 | -46 | 0 | 9
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1087 | 845 | 182 | 19 | 14.248 | 18 | 270.712 | 2018-05-16 | 2018-06-03 | 2018-07-01 | -28 | -6 | 1
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 846 | 192 | 10.441 | 14.248 | 18 | 148.7634 | 2018-05-16 | 2018-06-03 | 2018-07-01 | -28 | -5 | 2
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 791 | 832 | 6.662 | 14.583 | 36 | 97.1519 | 2018-05-16 | 2018-06-21 | 2018-07-28 | -37 | -6 | 0
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1088 | 790 | 822 | 16.055 | 14.575 | 36 | 234.0016 | 2018-05-10 | 2018-06-15 | 2018-07-28 | -43 | 0 | 0
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1088 | 774 | 271 | 17.8 | 16 | 32 | 284.8 | 2018-05-16 | 2018-06-17 | 2018-08-02 | -46 | 0 | 6
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 773 | 261 | 20.1 | 16 | 32 | 321.6 | 2018-05-16 | 2018-06-17 | 2018-08-02 | -46 | 0 | 6
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 798 | 125 | 9.8 | 18.5 | 34 | 181.3 | 2018-05-18 | 2018-06-21 | 2018-07-21 | -30 | -6 | 1
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1087 | 834 | 123 | 16.106 | 12.2 | 22 | 196.4932 | 2018-05-19 | 2018-06-10 | 2018-07-03 | -23 | -7 | 1
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 780 | 135 | 13.1 | 18.5 | 43 | 242.35 | 2018-05-20 | 2018-07-02 | 2018-08-09 | -38 | -8 | 1
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 835 | 133 | 24.07 | 12.2 | 22 | 293.654 | 2018-07-14 | 2018-08-05 | 2018-07-03 | 33 | -63 | 1
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 800 | 836 | 8 | 21 | 29 | 168 | 2018-05-20 | 2018-06-18 | 2018-07-15 | -27 | -6 | 3
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 799 | 826 | 20.5 | 21 | 29 | 430.5 | 2018-06-11 | 2018-07-10 | 2018-07-15 | -5 | -28 | 3
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 818 | 834 | 7.062 | 14.636 | 25 | 103.3594 | 2018-05-20 | 2018-06-14 | 2018-07-11 | -27 | -8 | 0
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1087 | 813 | 824 | 17.596 | 14.575 | 27 | 256.4617 | 2018-05-21 | 2018-06-17 | 2018-07-14 | -27 | -8 | 1
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1087 | 763 | 629 | 15.6 | 18.9 | 32 | 294.84 | 2018-05-23 | 2018-06-24 | 2018-08-07 | -44 | 0 | 11
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 764 | 639 | 15.6 | 18.9 | 32 | 294.84 | 2018-05-23 | 2018-06-24 | 2018-08-07 | -44 | 0 | 11
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 851 | 144 | 24.366 | 16.385 | 15 | 399.2369 | 2018-10-23 | 2018-11-07 | 2018-06-21 | 139 | -161 | 2
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 801 | 292 | 16.6 | 19.5 | 30 | 323.7 | 2018-05-24 | 2018-06-23 | 2018-07-22 | -29 | -3 | 6
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 806 | 282 | 14.7 | 19.5 | 30 | 286.65 | 2018-05-27 | 2018-06-26 | 2018-07-21 | -25 | -5 | 7
42 South-2 | BQM4202A | 18 | 18 | YT | H1087 | 785 | 122 | 12 | 12.3 | 28 | 147.6 | 2018-05-23 | 2018-06-20 | 2018-07-29 | -39 | 0 | 7
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1087 | 786 | 132 | 10.219 | 12.3 | 28 | 125.6937 | 2018-05-27 | 2018-06-24 | 2018-07-29 | -35 | -4 | 7
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1088 | 697 | 683 | 16.6 | 18.9 | 24 | 313.74 | 2018-06-01 | 2018-06-25 | 2018-08-28 | -64 | 0 | 16
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 698 | 693 | 16.6 | 18.9 | 24 | 313.74 | 2018-06-01 | 2018-06-25 | 2018-08-28 | -64 | 0 | 16
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 827 | 833 | 7.281 | 14.575 | 24 | 106.1206 | 2018-05-28 | 2018-06-21 | 2018-07-09 | -18 | -11 | 0
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1088 | 826 | 823 | 17.548 | 14.578 | 27 | 255.8147 | 2018-05-17 | 2018-06-13 | 2018-07-12 | -29 | 0 | 0
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 814 | 112 | 21 | 8.6 | 18 | 180.6 | 2018-06-01 | 2018-06-19 | 2018-07-04 | -15 | -10 | 5
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1088 | 755 | 269 | 10.5 | 18.9 | 29 | 198.45 | 2018-05-29 | 2018-06-27 | 2018-08-11 | -45 | -8 | 3
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 756 | 279 | 10.5 | 18.9 | 29 | 198.45 | 2018-05-30 | 2018-06-28 | 2018-08-11 | -44 | -9 | 3
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1088 | 855 | 834 | 9.215 | 10.9 | 19 | 100.4435 | 2018-06-01 | 2018-06-20 | 2018-07-01 | -11 | -10 | 4
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 854 | 824 | 15.665 | 11.094 | 19 | 173.7875 | 2018-06-01 | 2018-06-20 | 2018-07-01 | -11 | -10 | 4
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1087 | 736 | 101 | 11.523 | 8.65 | 28 | 99.674 | 2018-05-23 | 2018-06-20 | 2018-08-19 | -60 | 0 | 5
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 685 | 110 | 12 | 5.487 | 41 | 65.844 | 2018-06-01 | 2018-07-12 | 2018-09-03 | -53 | -8 | 5
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1088 | 808 | 653 | 11.2 | 17.72 | 16 | 198.464 | 2018-05-23 | 2018-06-08 | 2018-07-09 | -31 | 0 | 3
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1088 | 807 | 643 | 13.412 | 17.72 | 16 | 237.6606 | 2018-06-03 | 2018-06-19 | 2018-07-09 | -20 | -11 | 3
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 775 | 102 | 16.588 | 12.377 | 35 | 205.3097 | 2018-06-04 | 2018-07-09 | 2018-07-31 | -22 | -13 | 1
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 860 | 833 | 8.709 | 14.287 | 16 | 124.4255 | 2018-06-04 | 2018-06-20 | 2018-06-28 | -8 | -13 | 0
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 837 | 823 | 16.231 | 14.307 | 18 | 232.2169 | 2018-06-04 | 2018-06-22 | 2018-07-05 | -13 | -13 | 0
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 725 | 123 | 16.13 | 18.505 | 42 | 298.4857 | 2018-06-04 | 2018-07-16 | 2018-09-06 | -52 | -8 | 5
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 726 | 133 | 23.777 | 18.85 | 42 | 448.1965 | 2018-10-29 | 2018-12-10 | 2018-09-06 | 95 | -155 | 5
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 656 | 124 | 21 | 18.1 | 26 | 380.1 | 2018-06-06 | 2018-07-02 | 2018-09-12 | -72 | -7 | 7
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 657 | 134 | 21 | 18.1 | 26 | 380.1 | 2018-06-07 | 2018-07-03 | 2018-09-12 | -71 | -8 | 7
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1088 | 741 | 143 | 5.23 | 16.375 | 35 | 85.6412 | 2018-06-07 | 2018-07-12 | 2018-08-27 | -46 | -10 | 4
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1088 | 742 | 153 | 15 | 16.375 | 35 | 245.625 | 2018-06-07 | 2018-07-12 | 2018-08-27 | -46 | -10 | 4
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1087 | 781 | 142 | 16.252 | 5.15 | 30 | 83.6978 | 2018-05-31 | 2018-06-30 | 2018-08-04 | -35 | 0 | 5
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 782 | 152 | 16.252 | 5.15 | 30 | 83.6978 | 2018-06-08 | 2018-07-08 | 2018-08-04 | -27 | -8 | 5
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 671 | 183 | 11.2 | 20 | 35 | 224 | 2018-06-10 | 2018-07-15 | 2018-09-14 | -61 | -8 | 7
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 678 | 193 | 19.9 | 20 | 35 | 398 | 2018-06-11 | 2018-07-16 | 2018-09-13 | -59 | -8 | 8
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 746 | 103 | 24 | 11 | 38 | 264 | 2018-11-08 | 2018-12-16 | 2018-08-20 | 118 | -159 | 6
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 683 | 182 | 7.9 | 19.9 | 40 | 157.21 | 2018-06-11 | 2018-07-21 | 2018-09-18 | -59 | -7 | 8
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 684 | 192 | 23.8 | 19.9 | 40 | 473.62 | 2018-12-11 | 2019-01-20 | 2018-09-18 | 124 | -190 | 8
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 666 | 261 | 19.155 | 12.423 | 39 | 237.9626 | 2018-06-11 | 2018-07-20 | 2018-09-20 | -62 | -8 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 667 | 271 | 21.56 | 12.423 | 39 | 267.8399 | 2018-06-11 | 2018-07-20 | 2018-09-20 | -62 | -8 | 6
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1087 | 747 | 184 | 13.9 | 8.3 | 28 | 115.37 | 2018-06-11 | 2018-07-09 | 2018-08-12 | -34 | -7 | 7
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 748 | 194 | 18 | 8.3 | 28 | 149.4 | 2018-06-12 | 2018-07-10 | 2018-08-12 | -33 | -8 | 7
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 753 | 161 | 14.057 | 15.486 | 37 | 217.6867 | 2018-06-12 | 2018-07-19 | 2018-08-19 | -31 | -7 | 8
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 754 | 171 | 20.177 | 15.486 | 37 | 312.461 | 2018-06-05 | 2018-07-12 | 2018-08-19 | -38 | 0 | 8
45 South-4 | BQM4504A | 20 | 21 | ZH | H1087 | 636 | 144 | 15.117 | 16.07 | 25 | 242.9302 | 2018-06-12 | 2018-07-07 | 2018-09-18 | -73 | -9 | 5
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 643 | 154 | 19.39 | 16.07 | 24 | 311.5973 | 2018-06-12 | 2018-07-06 | 2018-09-16 | -72 | -9 | 5
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 595 | 283 | 18.4 | 18.9 | 43 | 347.76 | 2018-06-12 | 2018-07-25 | 2018-10-05 | -72 | -9 | 5
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 600 | 293 | 19.5 | 18.9 | 43 | 368.55 | 2018-06-13 | 2018-07-26 | 2018-10-02 | -68 | -10 | 5
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 596 | 294 | 20 | 18.4 | 45 | 368 | 2018-06-15 | 2018-07-30 | 2018-10-06 | -68 | -11 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 658 | 101 | 30.66 | 9.4 | 31 | 288.204 | 2018-12-17 | 2019-01-17 | 2018-09-15 | 124 | -195 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 659 | 101 | 30.66 | 9.4 | 31 | 288.204 | 2019-01-18 | 2019-02-18 | 2018-09-15 | 156 | -227 | 7
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 589 | 284 | 20 | 18.4 | 45 | 368 | 2018-06-18 | 2018-08-02 | 2018-10-07 | -66 | -13 | 7
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 679 | 272 | 15.89 | 20.773 | 33 | 330.083 | 2018-06-18 | 2018-07-21 | 2018-09-13 | -54 | -11 | 9
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 699 | 144 | 24.366 | 16.385 | 38 | 399.2369 | 2019-01-21 | 2019-02-28 | 2018-09-08 | 173 | -228 | 9
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 680 | 262 | 11.65 | 20.773 | 33 | 242.0054 | 2018-06-18 | 2018-07-21 | 2018-09-13 | -54 | -10 | 10
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 692 | 154 | 24.839 | 16.385 | 39 | 406.987 | 2019-02-19 | 2019-03-30 | 2018-09-11 | 200 | -256 | 10
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 768 | 101 | 13.007 | 16.37 | 22 | 212.9246 | 2018-06-19 | 2018-07-11 | 2018-07-19 | -8 | -18 | 2
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 668 | 112 | 20 | 5.15 | 41 | 103 | 2018-06-20 | 2018-07-31 | 2018-09-06 | -37 | -14 | 7
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1088 | 613 | 144 | 15.117 | 16.07 | 25 | 242.9302 | 2018-06-20 | 2018-07-15 | 2018-09-20 | -67 | -14 | 5
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1088 | 614 | 154 | 19.39 | 16.07 | 25 | 311.5973 | 2018-06-21 | 2018-07-16 | 2018-09-20 | -66 | -15 | 5
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 686 | 162 | 18.5 | 15.5 | 32 | 286.75 | 2018-06-21 | 2018-07-23 | 2018-09-06 | -45 | -12 | 8
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1088 | 615 | 172 | 18.5 | 15.698 | 32 | 290.413 | 2018-06-21 | 2018-07-23 | 2018-09-24 | -63 | -12 | 8
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 711 | 103 | 23.857 | 9.5 | 34 | 226.6415 | 2019-03-01 | 2019-04-04 | 2018-08-31 | 216 | -270 | 2
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1088 | 730 | 331 | 8.6 | 20.5 | 32 | 176.3 | 2018-06-22 | 2018-07-24 | 2018-08-29 | -36 | -10 | 10
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 729 | 321 | 14.8 | 20.5 | 32 | 303.4 | 2018-06-22 | 2018-07-24 | 2018-08-29 | -36 | -10 | 10
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 700 | 143 | 14.606 | 16.186 | 26 | 236.4127 | 2018-06-08 | 2018-07-04 | 2018-08-28 | -55 | 0 | 5
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 701 | 153 | 19.167 | 16.07 | 26 | 308.0137 | 2018-06-22 | 2018-07-18 | 2018-08-28 | -41 | -14 | 5
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 661 | 836 | 6.45 | 21.691 | 55 | 139.9069 | 2018-07-07 | 2018-08-31 | 2018-10-03 | -33 | -27 | 7
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1088 | 628 | 125 | 9.8 | 18.5 | 42 | 181.3 | 2018-06-10 | 2018-07-22 | 2018-10-04 | -74 | 0 | 7
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 629 | 135 | 13.1 | 18.5 | 42 | 242.35 | 2018-06-23 | 2018-08-04 | 2018-10-04 | -61 | -13 | 7
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 719 | 801 | 20.814 | 15.31 | 33 | 318.6623 | 2018-06-26 | 2018-07-29 | 2018-08-29 | -31 | -16 | 7
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 660 | 826 | 20.852 | 21.691 | 55 | 452.3007 | 2018-07-11 | 2018-09-04 | 2018-10-03 | -29 | -31 | 7
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 687 | 801 | 20.814 | 15.31 | 33 | 318.6623 | 2018-07-03 | 2018-08-05 | 2018-09-08 | -34 | -27 | 2
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 727 | 102 | 26.372 | 14.65 | 35 | 386.3498 | 2018-08-06 | 2018-09-10 | 2018-08-28 | 13 | -58 | 5
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 728 | 102 | 26.372 | 14.65 | 35 | 386.3498 | 2019-03-31 | 2019-05-05 | 2018-08-28 | 250 | -295 | 5
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 650 | 628 | 15.6 | 20 | 23 | 312 | 2018-06-24 | 2018-07-17 | 2018-09-12 | -57 | -13 | 7
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 651 | 638 | 15.6 | 20 | 23 | 312 | 2018-06-25 | 2018-07-18 | 2018-09-12 | -56 | -14 | 7
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 712 | 134 | 19.318 | 18.5 | 44 | 357.383 | 2018-06-25 | 2018-08-08 | 2018-09-10 | -33 | -14 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 720 | 103 | 23.857 | 9.5 | 34 | 226.6415 | 2019-04-05 | 2019-05-09 | 2018-08-29 | 253 | -299 | 5
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 713 | 124 | 16.142 | 18.85 | 44 | 304.2767 | 2018-06-26 | 2018-08-09 | 2018-09-10 | -32 | -14 | 7
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 705 | 123 | 20.9 | 18.1 | 28 | 378.29 | 2018-07-04 | 2018-08-01 | 2018-08-26 | -25 | -21 | 7
45 South-4 | BQM4504A | 20 | 21 | ZH | H1087 | 706 | 123 | 20.9 | 18.1 | 28 | 378.29 | 2018-07-08 | 2018-08-05 | 2018-08-26 | -21 | -25 | 7
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1088 | 707 | 133 | 21.1 | 18.1 | 28 | 381.91 | 2018-07-12 | 2018-08-09 | 2018-08-26 | -17 | -29 | 7
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 708 | 133 | 21.1 | 18.1 | 28 | 381.91 | 2018-07-16 | 2018-08-13 | 2018-08-26 | -13 | -33 | 7
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1088 | 745 | 104 | 18.3 | 18.2 | 21 | 333.06 | 2018-06-09 | 2018-06-30 | 2018-08-15 | -46 | 0 | 2
42 South-2 | BQM4202A | 18 | 18 | YT | H1087 | 731 | 101 | 11.523 | 8.65 | 28 | 99.674 | 2018-06-21 | 2018-07-19 | 2018-08-21 | -33 | -9 | 5
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 693 | 322 | 12.4 | 19.6 | 39 | 243.04 | 2018-06-27 | 2018-08-05 | 2018-09-10 | -36 | -18 | 1
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1088 | 694 | 332 | 12.4 | 19.6 | 39 | 243.04 | 2018-06-28 | 2018-08-06 | 2018-09-10 | -35 | -19 | 1
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1087 | 703 | 834 | 7.062 | 14.636 | 33 | 103.3594 | 2018-06-29 | 2018-08-01 | 2018-09-04 | -34 | -14 | 7
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 749 | 161 | 13.792 | 9.4 | 17 | 129.6448 | 2018-07-03 | 2018-07-20 | 2018-08-06 | -17 | -18 | 7
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 750 | 161 | 13.792 | 9.4 | 17 | 129.6448 | 2018-07-09 | 2018-07-26 | 2018-08-06 | -11 | -24 | 7
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 743 | 142 | 8.276 | 16.07 | 22 | 132.9953 | 2018-07-10 | 2018-08-01 | 2018-08-16 | -15 | -25 | 7
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 751 | 171 | 16.655 | 9.4 | 17 | 156.557 | 2018-07-10 | 2018-07-27 | 2018-08-06 | -10 | -25 | 7
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 752 | 171 | 16.655 | 9.4 | 17 | 156.557 | 2018-07-11 | 2018-07-28 | 2018-08-06 | -9 | -26 | 7
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1088 | 744 | 152 | 15.186 | 16.07 | 22 | 244.039 | 2018-07-13 | 2018-08-04 | 2018-08-16 | -12 | -28 | 7
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 702 | 824 | 17.596 | 14.575 | 33 | 256.4617 | 2018-07-13 | 2018-08-15 | 2018-09-04 | -20 | -28 | 7
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1088 | 709 | 173 | 16.387 | 11.151 | 22 | 182.7314 | 2018-06-16 | 2018-07-08 | 2018-08-24 | -47 | 0 | 8
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 704 | 163 | 16.387 | 11.151 | 22 | 182.7314 | 2018-07-13 | 2018-08-04 | 2018-08-25 | -21 | -26 | 8
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 733 | 835 | 5.59 | 17.008 | 26 | 95.0747 | 2018-07-16 | 2018-08-11 | 2018-08-20 | -9 | -31 | 5
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 732 | 825 | 17.18 | 16.97 | 26 | 291.5446 | 2018-07-17 | 2018-08-12 | 2018-08-20 | -8 | -32 | 5
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 740 | 832 | 14 | 10.3 | 22 | 144.2 | 2018-07-17 | 2018-08-08 | 2018-08-18 | -10 | -30 | 7
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 715 | 833 | 7.281 | 14.575 | 31 | 106.1206 | 2018-07-17 | 2018-08-17 | 2018-09-02 | -16 | -30 | 7
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 739 | 822 | 12.6 | 10.3 | 22 | 129.78 | 2018-07-18 | 2018-08-09 | 2018-08-18 | -9 | -31 | 7
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 737 | 142 | 8.276 | 16.07 | 22 | 132.9953 | 2018-07-19 | 2018-08-10 | 2018-08-18 | -8 | -32 | 7
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 738 | 152 | 15.186 | 16.07 | 22 | 244.039 | 2018-07-19 | 2018-08-10 | 2018-08-18 | -8 | -32 | 7
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 714 | 823 | 17.548 | 14.578 | 31 | 255.8147 | 2018-07-20 | 2018-08-20 | 2018-09-02 | -13 | -33 | 7
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1088 | 682 | 694 | 16.7 | 18.4 | 38 | 307.28 | 2018-06-17 | 2018-07-25 | 2018-09-16 | -53 | 0 | 7
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 681 | 684 | 17.5 | 18.4 | 38 | 322 | 2018-07-20 | 2018-08-27 | 2018-09-16 | -20 | -33 | 7
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 695 | 221 | 15 | 15.97 | 12 | 239.55 | 2018-07-21 | 2018-08-02 | 2018-08-28 | -26 | -38 | 1
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1088 | 696 | 221 | 16 | 15.97 | 12 | 255.52 | 2018-07-21 | 2018-08-02 | 2018-08-28 | -26 | -38 | 1
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 722 | 835 | 5.59 | 17.008 | 27 | 95.0747 | 2018-07-21 | 2018-08-17 | 2018-08-24 | -7 | -34 | 5
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 721 | 825 | 17.18 | 16.97 | 27 | 291.5446 | 2018-07-22 | 2018-08-18 | 2018-08-24 | -6 | -35 | 5
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1087 | 670 | 835 | 17 | 17.3 | 40 | 294.1 | 2018-07-22 | 2018-08-31 | 2018-09-22 | -22 | -33 | 7
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 735 | 832 | 13 | 10.3 | 22 | 133.9 | 2018-07-22 | 2018-08-13 | 2018-08-20 | -7 | -33 | 7
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 734 | 822 | 12.6 | 10.3 | 22 | 129.78 | 2018-07-24 | 2018-08-15 | 2018-08-20 | -5 | -35 | 7
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 669 | 825 | 18.455 | 17.3 | 40 | 319.2715 | 2018-07-24 | 2018-09-02 | 2018-09-22 | -20 | -35 | 7
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 688 | 231 | 14.308 | 15.97 | 14 | 228.4988 | 2018-07-25 | 2018-08-08 | 2018-08-30 | -22 | -38 | 4
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 689 | 231 | 14.308 | 15.97 | 14 | 228.4988 | 2018-07-25 | 2018-08-08 | 2018-08-30 | -22 | -38 | 4
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 716 | 834 | 25 | 13.72 | 26 | 343 | 2019-05-06 | 2019-06-01 | 2018-08-25 | 280 | -320 | 5
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 710 | 834 | 24 | 13.72 | 25 | 329.28 | 2019-05-10 | 2019-06-04 | 2018-08-26 | 282 | -321 | 5
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 665 | 832 | 6.662 | 14.583 | 35 | 97.1519 | 2018-07-26 | 2018-08-30 | 2018-09-20 | -21 | -31 | 7
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1088 | 664 | 822 | 16.055 | 14.575 | 35 | 234.0016 | 2018-06-25 | 2018-07-30 | 2018-09-20 | -52 | 0 | 7
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 723 | 182 | 18 | 14.248 | 19 | 256.464 | 2018-07-27 | 2018-08-15 | 2018-08-21 | -6 | -31 | 7
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 724 | 192 | 10.441 | 14.248 | 19 | 148.7634 | 2018-07-27 | 2018-08-15 | 2018-08-21 | -6 | -31 | 7
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 717 | 182 | 17 | 14.248 | 19 | 242.216 | 2018-07-28 | 2018-08-16 | 2018-08-22 | -6 | -31 | 7
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 718 | 192 | 10.441 | 14.248 | 19 | 148.7634 | 2018-06-27 | 2018-07-16 | 2018-08-22 | -37 | 0 | 7
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 672 | 122 | 15.531 | 12.2 | 17 | 189.4782 | 2018-07-29 | 2018-08-15 | 2018-08-31 | -16 | -32 | 7
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1087 | 673 | 122 | 15.531 | 12.2 | 17 | 189.4782 | 2018-06-27 | 2018-07-14 | 2018-08-31 | -48 | 0 | 7
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 674 | 132 | 18.94 | 12.2 | 17 | 231.068 | 2018-07-30 | 2018-08-16 | 2018-08-31 | -15 | -33 | 7
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 675 | 132 | 18.94 | 12.2 | 17 | 231.068 | 2018-07-31 | 2018-08-17 | 2018-08-31 | -14 | -34 | 7
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 690 | 143 | 14.606 | 16.186 | 26 | 236.4127 | 2018-08-01 | 2018-08-27 | 2018-08-31 | -4 | -36 | 5
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1088 | 691 | 153 | 19.167 | 16.07 | 26 | 308.0137 | 2018-06-26 | 2018-07-22 | 2018-08-31 | -40 | 0 | 5
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 481 | 836 | 6.45 | 21.691 | 54 | 139.9069 | 2018-08-03 | 2018-09-26 | 2018-11-19 | -54 | -35 | 7
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 480 | 826 | 20.852 | 21.691 | 54 | 452.3007 | 2018-09-05 | 2018-10-29 | 2018-11-19 | -21 | -68 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 676 | 103 | 29.101 | 15.68 | 16 | 456.3037 | 2019-06-02 | 2019-06-18 | 2018-08-30 | 292 | -338 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 677 | 103 | 29.101 | 15.68 | 16 | 456.3037 | 2019-06-05 | 2019-06-21 | 2018-08-30 | 295 | -341 | 7
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1087 | 639 | 271 | 15.2 | 18.8 | 34 | 285.76 | 2018-08-02 | 2018-09-05 | 2018-09-26 | -21 | -31 | 7
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1087 | 640 | 271 | 15.2 | 18.8 | 34 | 285.76 | 2018-08-02 | 2018-09-05 | 2018-09-26 | -21 | -31 | 7
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1087 | 637 | 261 | 20.5 | 18.8 | 34 | 385.4 | 2018-07-02 | 2018-08-05 | 2018-09-26 | -52 | 0 | 7
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 638 | 261 | 20.5 | 18.8 | 34 | 385.4 | 2018-08-02 | 2018-09-05 | 2018-09-26 | -21 | -31 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 585 | 111 | 22.2 | 13.8 | 25 | 306.36 | 2019-06-19 | 2019-07-14 | 2018-09-24 | 293 | -351 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 586 | 111 | 22.2 | 13.8 | 25 | 306.36 | 2019-06-22 | 2019-07-17 | 2018-09-24 | 296 | -354 | 7
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 616 | 632 | 13.38 | 17.28 | 14 | 231.2064 | 2018-08-03 | 2018-08-17 | 2018-09-14 | -28 | -32 | 4
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1088 | 617 | 632 | 13.38 | 17.28 | 14 | 231.2064 | 2018-08-03 | 2018-08-17 | 2018-09-14 | -28 | -32 | 4
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 641 | 622 | 13.38 | 17.28 | 13 | 231.2064 | 2018-08-05 | 2018-08-18 | 2018-09-11 | -24 | -33 | 5
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 642 | 622 | 13.38 | 17.28 | 13 | 231.2064 | 2018-08-05 | 2018-08-18 | 2018-09-11 | -24 | -33 | 5
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 630 | 629 | 15.6 | 18.9 | 32 | 294.84 | 2018-08-05 | 2018-09-06 | 2018-09-26 | -20 | -30 | 7
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 631 | 629 | 15.6 | 18.9 | 32 | 294.84 | 2018-08-06 | 2018-09-07 | 2018-09-26 | -19 | -31 | 7
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 632 | 639 | 15.6 | 18.9 | 32 | 294.84 | 2018-08-06 | 2018-09-07 | 2018-09-26 | -19 | -31 | 7
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1088 | 633 | 639 | 15.6 | 18.9 | 32 | 294.84 | 2018-08-06 | 2018-09-07 | 2018-09-26 | -19 | -31 | 7
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 529 | 102 | 22.89 | 15.65 | 47 | 358.2285 | 2018-09-11 | 2018-10-28 | 2018-10-22 | 6 | -67 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 557 | 144 | 17.566 | 15.678 | 23 | 275.3997 | 2018-08-07 | 2018-08-30 | 2018-10-07 | -38 | -31 | 7
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 558 | 144 | 17.566 | 15.678 | 23 | 275.3997 | 2018-08-09 | 2018-09-01 | 2018-10-07 | -36 | -33 | 7
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1087 | 559 | 154 | 19.932 | 15.976 | 23 | 318.4336 | 2018-08-09 | 2018-09-01 | 2018-10-07 | -36 | -33 | 7
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1087 | 560 | 154 | 19.932 | 15.976 | 23 | 318.4336 | 2018-08-09 | 2018-09-01 | 2018-10-07 | -36 | -33 | 7
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1087 | 574 | 101 | 11.577 | 13.021 | 45 | 150.7441 | 2018-07-07 | 2018-08-21 | 2018-10-19 | -59 | 0 | 6
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 618 | 268 | 10.8 | 20 | 30 | 216 | 2018-08-09 | 2018-09-08 | 2018-09-24 | -16 | -32 | 7
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 619 | 278 | 10.8 | 20 | 30 | 216 | 2018-07-08 | 2018-08-07 | 2018-09-24 | -48 | 0 | 7
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 590 | 183 | 8.82 | 15.798 | 21 | 139.3384 | 2018-08-10 | 2018-08-31 | 2018-09-24 | -24 | -35 | 4
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 591 | 193 | 15.59 | 15.978 | 21 | 249.097 | 2018-08-10 | 2018-08-31 | 2018-09-24 | -24 | -35 | 4
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 605 | 268 | 10.8 | 20 | 30 | 216 | 2018-08-10 | 2018-09-09 | 2018-09-25 | -16 | -32 | 7
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 606 | 278 | 10.8 | 20 | 30 | 216 | 2018-08-11 | 2018-09-10 | 2018-09-25 | -15 | -33 | 7
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 587 | 183 | 8.82 | 15.798 | 21 | 139.3384 | 2018-08-11 | 2018-09-01 | 2018-09-25 | -24 | -35 | 4
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 588 | 193 | 15.59 | 15.978 | 21 | 249.097 | 2018-08-12 | 2018-09-02 | 2018-09-25 | -23 | -36 | 4
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1088 | 644 | 143 | 13.809 | 15.686 | 21 | 216.608 | 2018-08-13 | 2018-09-03 | 2018-09-14 | -11 | -35 | 6
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 645 | 143 | 13.809 | 15.686 | 21 | 216.608 | 2018-08-14 | 2018-09-04 | 2018-09-14 | -10 | -36 | 6
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 562 | 124 | 18.618 | 14.354 | 22 | 267.2428 | 2018-08-14 | 2018-09-05 | 2018-10-04 | -29 | -36 | 6
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 563 | 124 | 18.618 | 14.354 | 22 | 267.2428 | 2018-08-16 | 2018-09-07 | 2018-10-04 | -27 | -38 | 6
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1088 | 646 | 153 | 18.919 | 15.5 | 21 | 293.2445 | 2018-07-09 | 2018-07-30 | 2018-09-14 | -46 | 0 | 6
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 647 | 153 | 18.919 | 15.5 | 21 | 293.2445 | 2018-08-16 | 2018-09-06 | 2018-09-14 | -8 | -38 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 564 | 134 | 22.828 | 14.354 | 22 | 327.6731 | 2019-07-15 | 2019-08-06 | 2018-10-04 | 306 | -371 | 6
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 565 | 134 | 22.828 | 14.354 | 22 | 327.6731 | 2018-10-29 | 2018-11-20 | 2018-10-04 | 47 | -112 | 6
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 634 | 124 | 21 | 18.1 | 26 | 380.1 | 2018-08-16 | 2018-09-11 | 2018-09-19 | -8 | -36 | 7
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 635 | 134 | 21 | 18.1 | 26 | 380.1 | 2018-08-17 | 2018-09-12 | 2018-09-19 | -7 | -37 | 7
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1088 | 601 | 269 | 10.5 | 18.9 | 29 | 198.45 | 2018-07-13 | 2018-08-11 | 2018-09-27 | -47 | 0 | 7
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1088 | 602 | 269 | 10.5 | 18.9 | 29 | 198.45 | 2018-08-16 | 2018-09-14 | 2018-09-27 | -13 | -34 | 7
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 603 | 279 | 10.5 | 18.9 | 29 | 198.45 | 2018-08-16 | 2018-09-14 | 2018-09-27 | -13 | -34 | 7
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 604 | 279 | 10.5 | 18.9 | 29 | 198.45 | 2018-08-17 | 2018-09-15 | 2018-09-27 | -12 | -35 | 7
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 535 | 834 | 7.062 | 14.636 | 34 | 103.3594 | 2018-08-18 | 2018-09-21 | 2018-10-25 | -34 | -35 | 7
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1088 | 534 | 824 | 17.596 | 14.575 | 34 | 256.4617 | 2018-08-18 | 2018-09-21 | 2018-10-25 | -34 | -35 | 7
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 648 | 628 | 15.6 | 20 | 23 | 312 | 2018-08-18 | 2018-09-10 | 2018-09-16 | -6 | -35 | 7
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 649 | 638 | 15.6 | 20 | 23 | 312 | 2018-08-18 | 2018-09-10 | 2018-09-16 | -6 | -35 | 7
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 543 | 833 | 7.281 | 14.575 | 32 | 106.1206 | 2018-08-18 | 2018-09-19 | 2018-10-23 | -34 | -33 | 7
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 599 | 824 | 14.342 | 13.72 | 26 | 196.7722 | 2018-08-19 | 2018-09-14 | 2018-09-24 | -10 | -34 | 7
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 542 | 823 | 17.548 | 14.578 | 32 | 255.8147 | 2018-08-19 | 2018-09-20 | 2018-10-23 | -33 | -34 | 7
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 652 | 102 | 19.76 | 18.47 | 20 | 364.9672 | 2018-08-19 | 2018-09-08 | 2018-09-05 | 3 | -40 | 0
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 653 | 102 | 19.76 | 18.47 | 20 | 364.9672 | 2018-08-28 | 2018-09-17 | 2018-09-05 | 12 | -49 | 0
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 598 | 824 | 14.342 | 13.72 | 26 | 196.7722 | 2018-08-21 | 2018-09-16 | 2018-09-25 | -9 | -35 | 7
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 620 | 621 | 8.95 | 15.97 | 14 | 142.9315 | 2018-08-28 | 2018-09-11 | 2018-09-14 | -3 | -48 | 0
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 621 | 621 | 8.95 | 15.97 | 14 | 142.9315 | 2018-08-31 | 2018-09-14 | 2018-09-14 | 0 | -51 | 0
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1087 | 607 | 631 | 10.53 | 15.97 | 13 | 168.1641 | 2018-08-31 | 2018-09-13 | 2018-09-14 | -1 | -51 | 0
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 608 | 631 | 10.53 | 15.97 | 13 | 168.1641 | 2018-09-01 | 2018-09-14 | 2018-09-14 | 0 | -52 | 0
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 581 | 272 | 14.4 | 17.28 | 31 | 248.832 | 2018-09-01 | 2018-10-02 | 2018-10-12 | -10 | -50 | 0
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 582 | 272 | 14.4 | 17.28 | 31 | 248.832 | 2018-09-01 | 2018-10-02 | 2018-10-12 | -10 | -50 | 0
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 579 | 262 | 14.6 | 17.28 | 31 | 252.288 | 2018-09-01 | 2018-10-02 | 2018-10-12 | -10 | -50 | 0
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1088 | 580 | 262 | 14.6 | 17.28 | 31 | 252.288 | 2018-09-02 | 2018-10-03 | 2018-10-12 | -9 | -51 | 0
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 662 | 183 | 7.507 | 14.276 | 20 | 107.1699 | 2018-09-02 | 2018-09-22 | 2018-09-10 | 12 | -46 | 5
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 663 | 193 | 14.445 | 14.246 | 20 | 205.7835 | 2018-09-02 | 2018-09-22 | 2018-09-10 | 12 | -46 | 5
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 494 | 835 | 16 | 17.3 | 39 | 276.8 | 2018-09-02 | 2018-10-11 | 2018-11-10 | -30 | -44 | 7
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 493 | 825 | 18.455 | 17.3 | 39 | 319.2715 | 2018-07-20 | 2018-08-28 | 2018-11-10 | -74 | 0 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 597 | 101 | 30.66 | 9.4 | 30 | 288.204 | 2019-07-18 | 2019-08-17 | 2018-09-27 | 324 | -368 | 0
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 654 | 183 | 7.507 | 14.276 | 19 | 107.1699 | 2018-09-03 | 2018-09-22 | 2018-09-10 | 12 | -45 | 5
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1087 | 655 | 193 | 14.445 | 14.246 | 19 | 205.7835 | 2018-07-20 | 2018-08-08 | 2018-09-10 | -33 | 0 | 5
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 592 | 231 | 14.308 | 15.97 | 21 | 228.4988 | 2018-07-29 | 2018-08-19 | 2018-10-01 | -43 | 0 | 14
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1088 | 538 | 283 | 13.7 | 18.32 | 31 | 250.984 | 2018-07-23 | 2018-08-23 | 2018-10-22 | -60 | -1 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 539 | 293 | 22.5 | 18.32 | 31 | 412.2 | 2019-08-07 | 2019-09-07 | 2018-10-22 | 320 | -381 | 6
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 497 | 832 | 6.662 | 14.583 | 35 | 97.1519 | 2018-09-03 | 2018-10-08 | 2018-11-05 | -28 | -42 | 7
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 496 | 822 | 16.055 | 14.575 | 35 | 234.0016 | 2018-09-04 | 2018-10-09 | 2018-11-05 | -27 | -43 | 7
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 584 | 221 | 14 | 15.97 | 20 | 223.58 | 2018-09-05 | 2018-09-25 | 2018-10-08 | -13 | -29 | 22
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 548 | 282 | 14.7 | 19.5 | 30 | 286.65 | 2018-09-06 | 2018-10-06 | 2018-10-21 | -15 | -45 | 6
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 549 | 292 | 16.6 | 19.5 | 30 | 323.7 | 2018-09-06 | 2018-10-06 | 2018-10-21 | -15 | -45 | 6
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 544 | 631 | 10.53 | 15.97 | 8 | 168.1641 | 2018-09-06 | 2018-09-14 | 2018-10-02 | -18 | -16 | 33
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 501 | 694 | 16.7 | 18.4 | 38 | 307.28 | 2018-09-06 | 2018-10-14 | 2018-11-05 | -22 | -41 | 7
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 500 | 684 | 17.5 | 18.4 | 38 | 322 | 2018-09-07 | 2018-10-15 | 2018-11-05 | -21 | -42 | 7
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1087 | 540 | 621 | 8.95 | 15.97 | 10 | 142.9315 | 2018-09-07 | 2018-09-17 | 2018-10-05 | -18 | -16 | 33
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 609 | 182 | 21 | 7.3 | 18 | 153.3 | 2018-09-08 | 2018-09-26 | 2018-09-19 | 7 | -45 | 4
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 610 | 182 | 22 | 7.3 | 18 | 160.6 | 2018-07-31 | 2018-08-18 | 2018-09-19 | -32 | -6 | 4
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 611 | 192 | 13.889 | 7.3 | 18 | 101.3897 | 2018-09-08 | 2018-09-26 | 2018-09-19 | 7 | -45 | 4
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 612 | 192 | 13.889 | 7.3 | 18 | 101.3897 | 2018-09-08 | 2018-09-26 | 2018-09-19 | 7 | -45 | 4
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 526 | 123 | 19.5 | 18.75 | 39 | 365.625 | 2018-09-08 | 2018-10-17 | 2018-10-27 | -10 | -43 | 6
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1088 | 423 | 110 | 16 | 4.932 | 51 | 78.912 | 2018-09-09 | 2018-10-30 | 2018-11-21 | -22 | -43 | 6
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 528 | 182 | 12.25 | 9.2 | 37 | 112.7 | 2018-09-09 | 2018-10-16 | 2018-10-24 | -8 | -43 | 6
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1088 | 570 | 271 | 17.8 | 16 | 31 | 284.8 | 2018-09-10 | 2018-10-11 | 2018-10-12 | -1 | -44 | 6
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 571 | 271 | 17.8 | 16 | 31 | 284.8 | 2018-09-11 | 2018-10-12 | 2018-10-12 | 0 | -45 | 6
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 568 | 261 | 20.1 | 16 | 31 | 321.6 | 2018-09-11 | 2018-10-12 | 2018-10-12 | 0 | -45 | 6
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 569 | 261 | 20.1 | 16 | 31 | 321.6 | 2018-09-11 | 2018-10-12 | 2018-10-12 | 0 | -45 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 566 | 111 | 22.2 | 13.8 | 25 | 306.36 | 2019-08-18 | 2019-09-12 | 2018-10-04 | 343 | -377 | 15
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 622 | 123 | 16.106 | 12.2 | 23 | 196.4932 | 2018-09-12 | 2018-10-05 | 2018-09-17 | 18 | -49 | 1
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1087 | 623 | 123 | 16.106 | 12.2 | 23 | 196.4932 | 2018-09-12 | 2018-10-05 | 2018-09-17 | 18 | -49 | 1
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 624 | 133 | 24.07 | 12.2 | 23 | 293.654 | 2019-09-08 | 2019-10-01 | 2018-09-17 | 379 | -410 | 1
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 625 | 133 | 24.07 | 12.2 | 23 | 293.654 | 2019-09-13 | 2019-10-06 | 2018-09-17 | 384 | -415 | 1
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1088 | 550 | 123 | 16.106 | 12.2 | 28 | 196.4932 | 2018-09-13 | 2018-10-11 | 2018-10-15 | -4 | -47 | 4
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 561 | 133 | 24.07 | 12.2 | 28 | 293.654 | 2019-10-02 | 2019-10-30 | 2018-10-11 | 384 | -431 | 4
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 567 | 102 | 19.76 | 18.47 | 38 | 364.9672 | 2018-09-14 | 2018-10-22 | 2018-10-17 | 5 | -49 | 0
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1088 | 502 | 192 | 16.9 | 9.2 | 37 | 155.48 | 2018-08-03 | 2018-09-09 | 2018-10-30 | -51 | 0 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1088 | 420 | 294 | 20 | 18.4 | 45 | 368 | 2018-09-15 | 2018-10-30 | 2018-11-27 | -28 | -42 | 7
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1088 | 419 | 284 | 20 | 18.4 | 45 | 368 | 2018-09-15 | 2018-10-30 | 2018-11-28 | -29 | -41 | 7
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 627 | 231 | 15.25 | 8.2 | 14 | 125.05 | 2018-09-15 | 2018-09-29 | 2018-09-16 | 13 | -41 | 6
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 626 | 221 | 18.25 | 8.2 | 14 | 149.65 | 2018-09-15 | 2018-09-29 | 2018-09-16 | 13 | -41 | 6
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 523 | 633 | 12.7 | 19.8 | 34 | 251.46 | 2018-09-15 | 2018-10-19 | 2018-10-26 | -7 | -41 | 6
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 522 | 623 | 13.6 | 19.8 | 34 | 269.28 | 2018-09-15 | 2018-10-19 | 2018-10-26 | -7 | -41 | 6
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 424 | 293 | 19.5 | 18.9 | 43 | 368.55 | 2018-09-16 | 2018-10-29 | 2018-11-25 | -27 | -41 | 7
42 South-2 | BQM4202A | 18 | 18 | YT | H1087 | 575 | 122 | 15.531 | 12.2 | 27 | 189.4782 | 2018-09-17 | 2018-10-14 | 2018-10-09 | 5 | -49 | -1
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 576 | 132 | 18.94 | 12.2 | 27 | 231.068 | 2018-09-18 | 2018-10-15 | 2018-10-09 | 6 | -50 | -1
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 438 | 111 | 11.85 | 25 | 40 | 296.25 | 2019-10-07 | 2019-11-16 | 2018-11-08 | 373 | -427 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 467 | 103 | 34.122 | 13.75 | 40 | 469.1775 | 2019-11-17 | 2019-12-27 | 2018-11-08 | 414 | -468 | 6
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1087 | 593 | 112 | 21 | 8.6 | 18 | 180.6 | 2018-09-18 | 2018-10-06 | 2018-09-18 | 18 | -43 | 5
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 594 | 112 | 21 | 8.6 | 18 | 180.6 | 2018-09-20 | 2018-10-08 | 2018-09-18 | 20 | -45 | 5
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 418 | 283 | 18.4 | 18.9 | 44 | 347.76 | 2018-09-21 | 2018-11-04 | 2018-11-29 | -25 | -44 | 7
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 545 | 273 | 14.5 | 18.79 | 26 | 272.455 | 2018-09-22 | 2018-10-18 | 2018-10-18 | 0 | -45 | 6
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 541 | 263 | 16.6 | 18.79 | 26 | 311.914 | 2018-09-22 | 2018-10-18 | 2018-10-19 | -1 | -45 | 6
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1088 | 583 | 112 | 21 | 8.6 | 18 | 180.6 | 2018-08-08 | 2018-08-26 | 2018-09-25 | -30 | 0 | 5
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 536 | 143 | 13.809 | 15.686 | 31 | 216.608 | 2018-09-23 | 2018-10-24 | 2018-10-23 | 1 | -44 | 7
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1088 | 537 | 153 | 18.919 | 15.5 | 31 | 293.2445 | 2018-09-23 | 2018-10-24 | 2018-10-23 | 1 | -44 | 7
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1087 | 509 | 683 | 16.6 | 18.9 | 24 | 313.74 | 2018-09-23 | 2018-10-17 | 2018-10-22 | -5 | -44 | 7
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 510 | 693 | 16.6 | 18.9 | 24 | 313.74 | 2018-09-26 | 2018-10-20 | 2018-10-22 | -2 | -47 | 7
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 516 | 124 | 18.618 | 14.354 | 32 | 267.2428 | 2018-09-27 | 2018-10-29 | 2018-10-29 | 0 | -45 | 10
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 517 | 134 | 22.828 | 14.354 | 32 | 327.6731 | 2019-10-31 | 2019-12-02 | 2018-10-29 | 399 | -444 | 10
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1087 | 555 | 632 | 13.38 | 17.28 | 16 | 231.2064 | 2018-09-27 | 2018-10-13 | 2018-10-06 | 7 | -43 | 12
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 531 | 632 | 13.5 | 20 | 29 | 270 | 2018-09-27 | 2018-10-26 | 2018-10-22 | 4 | -47 | 6
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 530 | 622 | 16.9 | 20 | 29 | 338 | 2018-09-27 | 2018-10-26 | 2018-10-22 | 4 | -47 | 6
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1087 | 556 | 622 | 13.38 | 17.28 | 15 | 231.2064 | 2018-08-17 | 2018-09-01 | 2018-10-05 | -34 | 0 | 12
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 553 | 182 | 20 | 7.3 | 17 | 146 | 2018-09-30 | 2018-10-17 | 2018-10-09 | 8 | -49 | 6
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 554 | 192 | 13.889 | 7.3 | 17 | 101.3897 | 2018-09-30 | 2018-10-17 | 2018-10-09 | 8 | -49 | 6
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 483 | 271 | 17.8 | 16 | 31 | 284.8 | 2018-10-03 | 2018-11-03 | 2018-11-05 | -2 | -52 | 6
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1087 | 482 | 261 | 20.1 | 16 | 31 | 321.6 | 2018-10-03 | 2018-11-03 | 2018-11-05 | -2 | -52 | 6
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 503 | 144 | 17.566 | 15.678 | 31 | 275.3997 | 2018-10-03 | 2018-11-03 | 2018-10-30 | 4 | -49 | 8
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1088 | 468 | 154 | 19.932 | 15.976 | 39 | 318.4336 | 2018-10-04 | 2018-11-12 | 2018-11-15 | -3 | -50 | 8
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 572 | 103 | 29.101 | 15.68 | 26 | 456.3037 | 2019-12-03 | 2019-12-29 | 2018-10-09 | 446 | -476 | 5
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1088 | 470 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2018-10-06 | 2018-10-31 | 2018-11-04 | -4 | -54 | 1
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 469 | 263 | 16.6 | 18.79 | 25 | 311.914 | 2018-10-06 | 2018-10-31 | 2018-11-04 | -4 | -54 | 1
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1087 | 513 | 835 | 7.416 | 16.884 | 20 | 125.2117 | 2018-10-07 | 2018-10-27 | 2018-10-18 | 9 | -50 | 6
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1087 | 514 | 835 | 7.416 | 16.884 | 20 | 125.2117 | 2018-10-07 | 2018-10-27 | 2018-10-18 | 9 | -50 | 6
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1087 | 511 | 825 | 19.167 | 16.931 | 20 | 324.5165 | 2018-08-18 | 2018-09-07 | 2018-10-18 | -41 | 0 | 6
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1087 | 512 | 825 | 19.167 | 16.931 | 20 | 324.5165 | 2018-10-07 | 2018-10-27 | 2018-10-18 | 9 | -50 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 460 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2018-10-09 | 2018-11-03 | 2018-11-05 | -2 | -56 | 1
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 459 | 263 | 16.6 | 18.79 | 25 | 311.914 | 2018-10-09 | 2018-11-03 | 2018-11-05 | -2 | -56 | 1
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 573 | 104 | 13.35 | 13.05 | 15 | 174.2175 | 2018-10-10 | 2018-10-25 | 2018-10-02 | 23 | -52 | 6
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 461 | 124 | 15.49 | 19.15 | 33 | 296.6335 | 2018-10-12 | 2018-11-14 | 2018-11-07 | 7 | -54 | 6
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 462 | 283 | 13.7 | 18.32 | 30 | 250.984 | 2018-10-12 | 2018-11-11 | 2018-11-08 | 3 | -53 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 450 | 293 | 22.5 | 18.32 | 30 | 412.2 | 2019-12-28 | 2020-01-27 | 2018-11-09 | 444 | -495 | 7
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 525 | 832 | 6.767 | 14.288 | 16 | 96.6869 | 2018-10-12 | 2018-10-28 | 2018-10-16 | 12 | -54 | 5
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 524 | 822 | 16.086 | 14.292 | 16 | 229.9011 | 2018-10-13 | 2018-10-29 | 2018-10-16 | 13 | -55 | 5
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 578 | 132 | 11 | 9.55 | 14 | 105.05 | 2018-10-13 | 2018-10-27 | 2018-10-01 | 26 | -54 | 6
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 577 | 122 | 18 | 9.55 | 14 | 171.9 | 2018-10-13 | 2018-10-27 | 2018-10-01 | 26 | -54 | 6
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 532 | 162 | 17.86 | 7.8 | 21 | 139.308 | 2018-10-14 | 2018-11-04 | 2018-10-15 | 20 | -55 | 6
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 533 | 172 | 18.45 | 12.45 | 21 | 229.7025 | 2018-10-15 | 2018-11-05 | 2018-10-15 | 21 | -56 | 6
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 504 | 662 | 14.6 | 20 | 27 | 292 | 2018-10-16 | 2018-11-12 | 2018-10-27 | 16 | -57 | 6
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 505 | 672 | 14.6 | 20 | 27 | 292 | 2018-10-16 | 2018-11-12 | 2018-10-27 | 16 | -57 | 6
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 451 | 134 | 18.74 | 19.44 | 33 | 364.3056 | 2018-10-17 | 2018-11-19 | 2018-11-08 | 11 | -58 | 6
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 446 | 193 | 20.1 | 20.9 | 35 | 420.09 | 2018-10-30 | 2018-12-04 | 2018-11-12 | 22 | -71 | 6
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 447 | 283 | 13.7 | 18.32 | 31 | 250.984 | 2018-10-18 | 2018-11-18 | 2018-11-11 | 7 | -58 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 445 | 293 | 22.5 | 18.32 | 31 | 412.2 | 2019-12-30 | 2020-01-30 | 2018-11-12 | 444 | -496 | 7
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1088 | 520 | 832 | 6.767 | 14.288 | 16 | 96.6869 | 2018-08-20 | 2018-09-05 | 2018-10-17 | -42 | 0 | 5
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 519 | 822 | 16.086 | 14.292 | 16 | 229.9011 | 2018-10-15 | 2018-10-31 | 2018-10-17 | 14 | -56 | 5
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 521 | 191 | 9 | 11.95 | 24 | 107.55 | 2018-10-18 | 2018-11-11 | 2018-10-22 | 20 | -58 | 6
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1088 | 506 | 143 | 10.97 | 13.152 | 25 | 144.2774 | 2018-10-18 | 2018-11-12 | 2018-10-24 | 19 | -58 | 6
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1087 | 507 | 153 | 18.861 | 13.05 | 25 | 246.1361 | 2018-10-18 | 2018-11-12 | 2018-10-24 | 19 | -58 | 6
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 518 | 181 | 15 | 11.95 | 24 | 179.25 | 2018-10-19 | 2018-11-12 | 2018-10-23 | 20 | -58 | 6
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 546 | 161 | 11.58 | 12.405 | 19 | 143.6499 | 2018-10-19 | 2018-11-07 | 2018-10-13 | 25 | -58 | 6
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1088 | 547 | 171 | 21.526 | 7.65 | 19 | 164.6739 | 2018-08-22 | 2018-09-10 | 2018-10-13 | -33 | 0 | 6
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 448 | 183 | 9.9 | 20.9 | 33 | 206.91 | 2018-08-22 | 2018-09-24 | 2018-11-10 | -47 | 0 | 6
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 463 | 125 | 14.8 | 19.15 | 31 | 283.42 | 2018-10-20 | 2018-11-20 | 2018-11-06 | 14 | -59 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 406 | 801 | 28.614 | 19.075 | 58 | 545.812 | 2020-01-28 | 2020-03-26 | 2018-12-29 | 453 | -527 | 2
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 551 | 623 | 13.38 | 18.79 | 15 | 251.4102 | 2018-10-20 | 2018-11-04 | 2018-10-08 | 27 | -61 | 3
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 552 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2018-10-21 | 2018-11-05 | 2018-10-08 | 28 | -62 | 3
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 452 | 803 | 15.5 | 20 | 29 | 310 | 2018-10-23 | 2018-11-21 | 2018-11-02 | 19 | -65 | 1
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1087 | 433 | 631 | 16.117 | 19.25 | 37 | 310.2523 | 2018-10-25 | 2018-12-01 | 2018-11-20 | 11 | -62 | 6
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 432 | 621 | 18.334 | 19.25 | 37 | 352.9295 | 2018-10-25 | 2018-12-01 | 2018-11-20 | 11 | -62 | 6
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 453 | 135 | 18.6 | 19.35 | 30 | 359.91 | 2018-10-27 | 2018-11-26 | 2018-11-06 | 20 | -64 | 6
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 449 | 803 | 15.5 | 19 | 29 | 294.5 | 2018-10-26 | 2018-11-24 | 2018-11-03 | 21 | -67 | 1
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1088 | 472 | 272 | 14.4 | 17.28 | 31 | 248.832 | 2018-10-27 | 2018-11-27 | 2018-11-10 | 17 | -63 | 6
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 471 | 262 | 14.6 | 17.28 | 31 | 252.288 | 2018-10-28 | 2018-11-28 | 2018-11-10 | 18 | -64 | 6
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 454 | 194 | 20.1 | 21.05 | 28 | 423.105 | 2018-12-05 | 2019-01-02 | 2018-11-04 | 59 | -101 | 6
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1087 | 498 | 183 | 8.82 | 15.798 | 22 | 139.3384 | 2018-10-28 | 2018-11-19 | 2018-10-24 | 26 | -62 | 6
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 455 | 184 | 9.804 | 21.05 | 27 | 206.3742 | 2018-10-28 | 2018-11-24 | 2018-11-03 | 21 | -62 | 6
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 499 | 193 | 15.59 | 15.978 | 22 | 249.097 | 2018-10-28 | 2018-11-19 | 2018-10-24 | 26 | -62 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 377 | 102 | 22.89 | 15.65 | 52 | 358.2285 | 2020-01-31 | 2020-03-23 | 2018-12-24 | 455 | -521 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 436 | 112 | 14.612 | 23 | 30 | 336.076 | 2020-03-24 | 2020-04-23 | 2018-11-11 | 529 | -573 | 6
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 402 | 101 | 11.577 | 13.021 | 49 | 150.7441 | 2018-10-28 | 2018-12-16 | 2018-12-19 | -3 | -60 | 6
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1088 | 484 | 623 | 13.38 | 18.79 | 15 | 251.4102 | 2018-08-24 | 2018-09-08 | 2018-10-25 | -47 | 0 | 0
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1088 | 485 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2018-10-29 | 2018-11-13 | 2018-10-25 | 19 | -66 | 0
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 476 | 623 | 13.38 | 18.79 | 15 | 251.4102 | 2018-10-30 | 2018-11-14 | 2018-10-26 | 19 | -66 | 0
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 477 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2018-10-30 | 2018-11-14 | 2018-10-26 | 19 | -66 | 0
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 489 | 155 | 14.7 | 13.05 | 22 | 191.835 | 2018-10-30 | 2018-11-21 | 2018-10-28 | 24 | -60 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 495 | 144 | 10.5 | 13.05 | 20 | 137.025 | 2018-10-31 | 2018-11-20 | 2018-10-25 | 26 | -60 | 6
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1088 | 456 | 671 | 18.6 | 14.9 | 25 | 277.14 | 2018-10-31 | 2018-11-25 | 2018-11-04 | 21 | -60 | 6
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 478 | 642 | 13.412 | 19.5 | 16 | 261.534 | 2018-10-31 | 2018-11-16 | 2018-10-27 | 20 | -60 | 5
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 479 | 652 | 13.412 | 19.5 | 16 | 261.534 | 2018-11-01 | 2018-11-17 | 2018-10-27 | 21 | -61 | 5
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 490 | 154 | 14.94 | 13.05 | 20 | 194.967 | 2018-11-01 | 2018-11-21 | 2018-10-26 | 26 | -60 | 6
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 473 | 642 | 13.412 | 19.5 | 16 | 261.534 | 2018-11-01 | 2018-11-17 | 2018-10-28 | 20 | -60 | 5
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 474 | 652 | 13.412 | 19.5 | 16 | 261.534 | 2018-11-04 | 2018-11-20 | 2018-10-28 | 23 | -63 | 5
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 486 | 145 | 10.1 | 13.065 | 20 | 131.9565 | 2018-11-04 | 2018-11-24 | 2018-10-27 | 28 | -62 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 408 | 801 | 28.614 | 19.075 | 37 | 545.812 | 2020-03-27 | 2020-05-03 | 2018-12-05 | 515 | -567 | 9
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 407 | 801 | 28.614 | 19.075 | 37 | 545.812 | 2020-04-24 | 2020-05-31 | 2018-12-06 | 542 | -594 | 9
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 441 | 836 | 8 | 21 | 33 | 168 | 2018-11-04 | 2018-12-07 | 2018-11-13 | 24 | -61 | 3
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1088 | 442 | 836 | 8 | 21 | 33 | 168 | 2018-11-04 | 2018-12-07 | 2018-11-13 | 24 | -61 | 3
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 439 | 826 | 20.5 | 21 | 33 | 430.5 | 2018-11-21 | 2018-12-24 | 2018-11-13 | 41 | -78 | 3
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 440 | 826 | 20.5 | 21 | 33 | 430.5 | 2019-01-03 | 2019-02-05 | 2018-11-13 | 84 | -121 | 3
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 427 | 661 | 18.6 | 14.9 | 29 | 277.14 | 2018-11-04 | 2018-12-03 | 2018-11-19 | 14 | -57 | 6
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1088 | 426 | 834 | 9.215 | 10.9 | 19 | 100.4435 | 2018-11-05 | 2018-11-24 | 2018-11-14 | 10 | -56 | 6
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 425 | 824 | 15.665 | 11.094 | 19 | 173.7875 | 2018-11-05 | 2018-11-24 | 2018-11-14 | 10 | -56 | 6
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1087 | 430 | 832 | 6.767 | 14.288 | 18 | 96.6869 | 2018-09-11 | 2018-09-29 | 2018-11-13 | -45 | 0 | 6
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 431 | 833 | 8.709 | 14.287 | 18 | 124.4255 | 2018-11-05 | 2018-11-23 | 2018-11-13 | 10 | -55 | 6
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 428 | 822 | 16.086 | 14.292 | 18 | 229.9011 | 2018-11-06 | 2018-11-24 | 2018-11-13 | 11 | -56 | 6
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 429 | 823 | 16.231 | 14.307 | 18 | 232.2169 | 2018-11-06 | 2018-11-24 | 2018-11-13 | 11 | -56 | 6
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 434 | 803 | 15.5 | 18 | 32 | 279 | 2018-11-08 | 2018-12-10 | 2018-11-14 | 26 | -62 | 1
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 437 | 292 | 16.6 | 19.5 | 34 | 323.7 | 2018-11-12 | 2018-12-16 | 2018-11-21 | 25 | -61 | 6
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 444 | 282 | 14.7 | 19.5 | 32 | 286.65 | 2018-11-12 | 2018-12-14 | 2018-11-17 | 27 | -59 | 7
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 435 | 292 | 16.6 | 19.5 | 33 | 323.7 | 2018-11-13 | 2018-12-16 | 2018-11-21 | 25 | -60 | 6
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 443 | 282 | 14.7 | 19.5 | 32 | 286.65 | 2018-11-13 | 2018-12-15 | 2018-11-18 | 27 | -59 | 7
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 415 | 836 | 8 | 21 | 31 | 168 | 2018-11-13 | 2018-12-14 | 2018-11-23 | 21 | -58 | 8
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 414 | 826 | 20.5 | 21 | 31 | 430.5 | 2019-02-06 | 2019-03-09 | 2018-11-23 | 106 | -143 | 8
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 465 | 653 | 11.2 | 17.72 | 16 | 198.464 | 2018-11-13 | 2018-11-29 | 2018-10-29 | 31 | -62 | 3
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 464 | 643 | 13.412 | 17.72 | 16 | 237.6606 | 2018-11-13 | 2018-11-29 | 2018-10-29 | 31 | -62 | 3
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 398 | 825 | 24.4 | 10.4 | 33 | 253.76 | 2020-05-04 | 2020-06-06 | 2018-12-12 | 542 | -584 | 19
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1087 | 492 | 834 | 9.215 | 10.9 | 22 | 100.4435 | 2018-11-13 | 2018-12-05 | 2018-10-30 | 36 | -60 | 4
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 491 | 824 | 15.665 | 11.094 | 22 | 173.7875 | 2018-11-14 | 2018-12-06 | 2018-10-30 | 37 | -61 | 4
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1088 | 458 | 653 | 11.2 | 17.72 | 15 | 198.464 | 2018-11-15 | 2018-11-30 | 2018-10-29 | 32 | -62 | 3
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1088 | 457 | 643 | 13.412 | 17.72 | 15 | 237.6606 | 2018-09-14 | 2018-09-29 | 2018-10-29 | -30 | 0 | 3
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 488 | 834 | 9.215 | 10.9 | 22 | 100.4435 | 2018-11-15 | 2018-12-07 | 2018-10-31 | 37 | -61 | 4
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1088 | 487 | 824 | 15.665 | 11.094 | 22 | 173.7875 | 2018-11-15 | 2018-12-07 | 2018-10-31 | 37 | -61 | 4
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1088 | 390 | 182 | 12.25 | 9.2 | 41 | 112.7 | 2018-11-17 | 2018-12-28 | 2018-12-22 | 6 | -61 | 6
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1088 | 378 | 123 | 19.5 | 18.75 | 43 | 365.625 | 2018-11-18 | 2018-12-31 | 2018-12-27 | 4 | -61 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 379 | 133 | 25.083 | 18.75 | 43 | 470.3062 | 2020-06-01 | 2020-07-14 | 2018-12-27 | 565 | -622 | 6
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 394 | 833 | 24 | 15.6 | 30 | 374.4 | 2018-12-25 | 2019-01-24 | 2018-12-12 | 43 | -78 | 26
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 393 | 823 | 21.1 | 15.6 | 30 | 329.16 | 2018-11-18 | 2018-12-18 | 2018-12-12 | 6 | -41 | 26
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 403 | 824 | 24.1 | 17.41 | 34 | 419.581 | 2019-01-25 | 2019-02-28 | 2018-12-05 | 85 | -128 | 6
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 515 | 833 | 8.709 | 14.287 | 15 | 124.4255 | 2018-11-19 | 2018-12-04 | 2018-10-19 | 46 | -66 | 0
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1087 | 475 | 823 | 16.231 | 14.307 | 21 | 232.2169 | 2018-09-14 | 2018-10-05 | 2018-11-03 | -29 | 0 | 0
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1087 | 508 | 833 | 8.709 | 14.287 | 15 | 124.4255 | 2018-11-20 | 2018-12-05 | 2018-10-20 | 46 | -66 | 0
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1087 | 466 | 823 | 16.231 | 14.307 | 21 | 232.2169 | 2018-09-15 | 2018-10-06 | 2018-11-04 | -29 | 0 | 0
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 330 | 110 | 15 | 4.932 | 54 | 73.98 | 2018-11-20 | 2019-01-13 | 2019-01-21 | -8 | -60 | 6
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 413 | 834 | 20 | 16.8 | 33 | 336 | 2018-11-20 | 2018-12-23 | 2018-11-25 | 28 | -60 | 6
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 373 | 192 | 16.9 | 9.2 | 41 | 155.48 | 2018-11-21 | 2019-01-01 | 2018-12-28 | 4 | -59 | 6
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 412 | 653 | 11.2 | 17.72 | 19 | 198.464 | 2018-09-23 | 2018-10-12 | 2018-11-21 | -40 | 0 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 417 | 643 | 13.412 | 17.72 | 19 | 237.6606 | 2018-11-21 | 2018-12-10 | 2018-11-18 | 22 | -59 | 6
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 411 | 652 | 13.412 | 19.5 | 19 | 261.534 | 2018-11-21 | 2018-12-10 | 2018-11-21 | 19 | -59 | 6
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 416 | 642 | 13.412 | 19.5 | 19 | 261.534 | 2018-11-22 | 2018-12-11 | 2018-11-18 | 23 | -60 | 6
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1087 | 400 | 832 | 22 | 15.4 | 24 | 338.8 | 2018-11-22 | 2018-12-16 | 2018-12-06 | 10 | -40 | 25
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 399 | 822 | 19.175 | 15.4 | 24 | 295.295 | 2018-11-24 | 2018-12-18 | 2018-12-06 | 12 | -42 | 25
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 351 | 111 | 11.85 | 24 | 44 | 284.4 | 2020-06-07 | 2020-07-21 | 2019-01-06 | 562 | -620 | 6
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 381 | 633 | 12.7 | 19.8 | 38 | 251.46 | 2018-11-25 | 2019-01-02 | 2018-12-25 | 8 | -60 | 6
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 380 | 623 | 13.6 | 19.8 | 38 | 269.28 | 2018-11-25 | 2019-01-02 | 2018-12-25 | 8 | -60 | 6
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 372 | 835 | 13.5 | 10.4 | 32 | 140.4 | 2018-11-22 | 2018-12-24 | 2018-12-21 | 3 | -44 | 19
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 395 | 845 | 18.075 | 12.65 | 31 | 228.6488 | 2018-11-25 | 2018-12-26 | 2018-12-12 | 14 | -44 | 21
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 353 | 801 | 24.3 | 17 | 47 | 413.1 | 2020-07-15 | 2020-08-31 | 2019-01-13 | 596 | -661 | 1
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 422 | 231 | 15.25 | 8.2 | 17 | 125.05 | 2018-11-25 | 2018-12-12 | 2018-11-15 | 27 | -58 | 6
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1088 | 421 | 221 | 18.25 | 8.2 | 17 | 149.65 | 2018-09-28 | 2018-10-15 | 2018-11-15 | -31 | 0 | 6
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 385 | 855 | 14 | 12.6 | 31 | 176.4 | 2018-10-13 | 2018-11-13 | 2018-12-14 | -31 | 0 | 21
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 357 | 103 | 34.122 | 13.75 | 43 | 469.1775 | 2020-07-22 | 2020-09-03 | 2019-01-07 | 605 | -662 | 6
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 382 | 683 | 17.8 | 14.8 | 32 | 263.44 | 2018-11-25 | 2018-12-27 | 2018-12-18 | 9 | -36 | 26
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 383 | 693 | 17.8 | 14.8 | 32 | 263.44 | 2018-11-25 | 2018-12-27 | 2018-12-18 | 9 | -36 | 26
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 386 | 643 | 19.9 | 14.2 | 26 | 282.58 | 2018-11-25 | 2018-12-21 | 2018-12-14 | 7 | -33 | 27
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 384 | 653 | 17.9 | 14.2 | 26 | 254.18 | 2018-11-26 | 2018-12-22 | 2018-12-15 | 7 | -33 | 27
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 410 | 835 | 7.416 | 16.884 | 25 | 125.2117 | 2018-11-27 | 2018-12-22 | 2018-11-24 | 28 | -60 | 0
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1088 | 409 | 825 | 19.167 | 16.931 | 25 | 324.5165 | 2018-11-28 | 2018-12-23 | 2018-11-24 | 29 | -61 | 0
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 392 | 632 | 13.5 | 20 | 29 | 270 | 2018-11-29 | 2018-12-28 | 2018-12-17 | 11 | -54 | 6
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 391 | 622 | 16.9 | 20 | 29 | 338 | 2018-11-30 | 2018-12-29 | 2018-12-17 | 12 | -55 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 324 | 101 | 30.66 | 9.4 | 30 | 288.204 | 2020-09-01 | 2020-10-01 | 2019-01-15 | 625 | -695 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 325 | 101 | 30.66 | 9.4 | 30 | 288.204 | 2020-09-04 | 2020-10-04 | 2019-01-15 | 628 | -698 | 7
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 360 | 193 | 20.1 | 20.9 | 35 | 420.09 | 2019-03-10 | 2019-04-14 | 2019-01-04 | 100 | -149 | 6
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 363 | 124 | 15.49 | 19.15 | 32 | 296.6335 | 2018-11-30 | 2019-01-01 | 2018-12-30 | 2 | -48 | 6
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1088 | 361 | 183 | 9.9 | 20.9 | 33 | 206.91 | 2018-12-02 | 2019-01-04 | 2019-01-02 | 2 | -49 | 6
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1088 | 374 | 662 | 14.6 | 20 | 27 | 292 | 2018-12-01 | 2018-12-28 | 2018-12-21 | 7 | -48 | 6
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 375 | 672 | 14.6 | 20 | 27 | 292 | 2018-12-02 | 2018-12-29 | 2018-12-21 | 8 | -49 | 6
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1088 | 387 | 191 | 9 | 11.95 | 23 | 107.55 | 2018-12-04 | 2018-12-27 | 2018-12-14 | 13 | -50 | 6
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 401 | 104 | 13.35 | 13.05 | 15 | 174.2175 | 2018-12-05 | 2018-12-20 | 2018-11-28 | 22 | -51 | 6
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 356 | 134 | 18.74 | 19.44 | 33 | 364.3056 | 2018-12-06 | 2019-01-08 | 2019-01-03 | 5 | -52 | 6
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 405 | 132 | 10 | 9.55 | 14 | 95.5 | 2018-12-06 | 2018-12-20 | 2018-11-27 | 23 | -51 | 6
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1088 | 376 | 181 | 14 | 11.95 | 24 | 167.3 | 2018-10-16 | 2018-11-09 | 2018-12-17 | -38 | 0 | 6
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1088 | 404 | 122 | 17 | 9.55 | 14 | 162.35 | 2018-12-07 | 2018-12-21 | 2018-11-27 | 24 | -52 | 6
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 388 | 162 | 17.86 | 7.8 | 21 | 139.308 | 2018-12-08 | 2018-12-29 | 2018-12-11 | 18 | -53 | 6
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1088 | 389 | 172 | 18.45 | 12.45 | 21 | 229.7025 | 2018-12-08 | 2018-12-29 | 2018-12-11 | 18 | -53 | 6
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 362 | 125 | 14.8 | 19.15 | 31 | 283.42 | 2018-12-08 | 2019-01-08 | 2018-12-31 | 8 | -53 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 369 | 143 | 10.97 | 13.152 | 25 | 144.2774 | 2018-12-08 | 2019-01-02 | 2018-12-20 | 13 | -52 | 6
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 370 | 153 | 18.861 | 13.05 | 25 | 246.1361 | 2018-12-11 | 2019-01-05 | 2018-12-20 | 16 | -55 | 6
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1088 | 358 | 135 | 18.6 | 19.35 | 31 | 359.91 | 2018-10-17 | 2018-11-17 | 2019-01-01 | -45 | 0 | 6
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 364 | 194 | 20.1 | 21.05 | 28 | 423.105 | 2019-04-15 | 2019-05-13 | 2018-12-26 | 138 | -180 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 396 | 161 | 11.58 | 12.405 | 18 | 143.6499 | 2018-12-11 | 2018-12-29 | 2018-12-08 | 21 | -53 | 6
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 397 | 171 | 21.526 | 7.65 | 18 | 164.6739 | 2018-12-15 | 2019-01-02 | 2018-12-08 | 25 | -57 | 6
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1087 | 365 | 184 | 9.804 | 21.05 | 26 | 206.3742 | 2018-12-17 | 2019-01-12 | 2018-12-24 | 19 | -59 | 6
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1088 | 340 | 631 | 16.117 | 19.25 | 37 | 310.2523 | 2018-10-19 | 2018-11-25 | 2019-01-15 | -51 | 0 | 6
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1088 | 339 | 621 | 18.334 | 19.25 | 37 | 352.9295 | 2018-12-11 | 2019-01-17 | 2019-01-15 | 2 | -53 | 6
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 354 | 221 | 20 | 15.97 | 12 | 319.4 | 2018-12-12 | 2018-12-24 | 2018-12-30 | -6 | -58 | 1
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1088 | 355 | 221 | 21 | 15.97 | 12 | 335.37 | 2018-12-15 | 2018-12-27 | 2018-12-30 | -3 | -61 | 1
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1087 | 333 | 684 | 14.7 | 20 | 35 | 294 | 2018-12-13 | 2019-01-17 | 2019-01-19 | -2 | -48 | 12
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 336 | 694 | 14.7 | 20 | 35 | 294 | 2018-12-16 | 2019-01-20 | 2019-01-18 | 2 | -51 | 12
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 349 | 231 | 14.308 | 15.97 | 14 | 228.4988 | 2018-10-19 | 2018-11-02 | 2019-01-01 | -60 | 0 | 4
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 350 | 231 | 14.308 | 15.97 | 14 | 228.4988 | 2018-12-17 | 2018-12-31 | 2019-01-01 | -1 | -59 | 4
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 341 | 112 | 14.612 | 22 | 30 | 321.464 | 2018-12-17 | 2019-01-16 | 2019-01-06 | 10 | -54 | 6
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 368 | 155 | 14.7 | 13.05 | 23 | 191.835 | 2018-12-17 | 2019-01-09 | 2018-12-23 | 17 | -54 | 6
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 371 | 144 | 10.5 | 13.05 | 19 | 137.025 | 2018-12-19 | 2019-01-07 | 2018-12-17 | 21 | -54 | 6
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 359 | 671 | 18.6 | 14.9 | 25 | 277.14 | 2018-12-19 | 2019-01-13 | 2018-12-29 | 15 | -54 | 6
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 342 | 122 | 15.531 | 12.2 | 16 | 189.4782 | 2018-12-21 | 2019-01-06 | 2018-12-29 | 8 | -55 | 7
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 343 | 122 | 15.531 | 12.2 | 16 | 189.4782 | 2018-12-21 | 2019-01-06 | 2018-12-29 | 8 | -55 | 7
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 344 | 132 | 18.94 | 12.2 | 16 | 231.068 | 2018-12-22 | 2019-01-07 | 2018-12-29 | 9 | -56 | 7
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1088 | 345 | 132 | 18.94 | 12.2 | 16 | 231.068 | 2018-12-22 | 2019-01-07 | 2018-12-29 | 9 | -56 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 346 | 103 | 29.101 | 15.68 | 16 | 456.3037 | 2020-10-02 | 2020-10-18 | 2018-12-29 | 659 | -705 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 347 | 103 | 29.101 | 15.68 | 16 | 456.3037 | 2020-10-05 | 2020-10-21 | 2018-12-29 | 662 | -708 | 7
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 366 | 145 | 10.1 | 13.065 | 20 | 131.9565 | 2018-12-23 | 2019-01-12 | 2018-12-21 | 22 | -56 | 6
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 367 | 154 | 14.94 | 13.05 | 20 | 194.967 | 2018-10-28 | 2018-11-17 | 2018-12-21 | -34 | 0 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 279 | 111 | 22.2 | 13.8 | 25 | 306.36 | 2020-10-19 | 2020-11-13 | 2019-01-20 | 663 | -721 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 280 | 111 | 22.2 | 13.8 | 25 | 306.36 | 2020-10-22 | 2020-11-16 | 2019-01-20 | 666 | -724 | 7
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 266 | 654 | 19.2 | 15.1 | 31 | 289.92 | 2018-12-23 | 2019-01-23 | 2019-01-31 | -8 | -35 | 27
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 265 | 644 | 22.9 | 15.1 | 31 | 345.79 | 2020-11-14 | 2020-12-15 | 2019-01-31 | 684 | -727 | 27
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 307 | 632 | 13.38 | 17.28 | 14 | 231.2064 | 2018-12-24 | 2019-01-07 | 2019-01-09 | -2 | -58 | 4
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1088 | 308 | 632 | 13.38 | 17.28 | 14 | 231.2064 | 2018-12-24 | 2019-01-07 | 2019-01-09 | -2 | -58 | 4
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 326 | 622 | 13.38 | 17.28 | 13 | 231.2064 | 2018-12-25 | 2019-01-07 | 2019-01-06 | 1 | -58 | 5
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 327 | 622 | 13.38 | 17.28 | 13 | 231.2064 | 2018-12-25 | 2019-01-07 | 2019-01-06 | 1 | -58 | 5
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 292 | 825 | 24.4 | 10.4 | 30 | 253.76 | 2020-11-17 | 2020-12-17 | 2019-01-19 | 698 | -737 | 19
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 288 | 833 | 23 | 15.6 | 30 | 358.8 | 2020-12-16 | 2021-01-15 | 2019-01-23 | 723 | -758 | 26
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 287 | 823 | 21.1 | 15.6 | 30 | 329.16 | 2018-12-28 | 2019-01-27 | 2019-01-23 | 4 | -39 | 26
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 213 | 101 | 30.66 | 9.4 | 30 | 288.204 | 2020-12-18 | 2021-01-17 | 2019-02-10 | 707 | -777 | 7
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 214 | 101 | 30.66 | 9.4 | 30 | 288.204 | 2019-03-01 | 2019-03-31 | 2019-02-10 | 49 | -119 | 7
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 348 | 661 | 18.6 | 14.9 | 25 | 277.14 | 2018-12-27 | 2019-01-21 | 2019-01-05 | 16 | -55 | 6
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 221 | 144 | 17.566 | 15.678 | 23 | 275.3997 | 2018-12-28 | 2019-01-20 | 2019-02-03 | -14 | -55 | 7
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 222 | 144 | 17.566 | 15.678 | 23 | 275.3997 | 2018-12-28 | 2019-01-20 | 2019-02-03 | -14 | -55 | 7
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1087 | 223 | 154 | 19.932 | 15.976 | 23 | 318.4336 | 2018-11-03 | 2018-11-26 | 2019-02-03 | -69 | 0 | 7
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 224 | 154 | 19.932 | 15.976 | 23 | 318.4336 | 2018-12-28 | 2019-01-20 | 2019-02-03 | -14 | -55 | 7
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1088 | 281 | 183 | 8.82 | 15.798 | 21 | 139.3384 | 2018-12-29 | 2019-01-19 | 2019-01-21 | -2 | -57 | 4
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 282 | 183 | 8.82 | 15.798 | 21 | 139.3384 | 2018-12-29 | 2019-01-19 | 2019-01-21 | -2 | -57 | 4
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 283 | 193 | 15.59 | 15.978 | 21 | 249.097 | 2018-12-29 | 2019-01-19 | 2019-01-21 | -2 | -57 | 4
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 284 | 193 | 15.59 | 15.978 | 21 | 249.097 | 2018-12-30 | 2019-01-20 | 2019-01-21 | -1 | -58 | 4
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 229 | 124 | 18.618 | 14.354 | 22 | 267.2428 | 2018-12-30 | 2019-01-21 | 2019-01-30 | -9 | -56 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1088 | 230 | 124 | 18.618 | 14.354 | 22 | 267.2428 | 2018-12-30 | 2019-01-21 | 2019-01-30 | -9 | -56 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 231 | 134 | 22.828 | 14.354 | 22 | 327.6731 | 2021-01-16 | 2021-02-07 | 2019-01-30 | 739 | -804 | 6
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 232 | 134 | 22.828 | 14.354 | 22 | 327.6731 | 2019-04-01 | 2019-04-23 | 2019-01-30 | 83 | -148 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 332 | 824 | 24.1 | 17.41 | 30 | 419.581 | 2021-01-18 | 2021-02-17 | 2019-01-12 | 767 | -806 | 6
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1087 | 352 | 834 | 19 | 16.8 | 30 | 319.2 | 2018-12-30 | 2019-01-29 | 2019-01-03 | 26 | -55 | 6
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 317 | 143 | 13.809 | 15.686 | 21 | 216.608 | 2018-12-30 | 2019-01-20 | 2019-01-11 | 9 | -55 | 6
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 318 | 143 | 13.809 | 15.686 | 21 | 216.608 | 2019-01-01 | 2019-01-22 | 2019-01-11 | 11 | -57 | 6
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 319 | 153 | 18.919 | 15.5 | 21 | 293.2445 | 2019-01-01 | 2019-01-22 | 2019-01-11 | 11 | -57 | 6
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1087 | 320 | 153 | 18.919 | 15.5 | 21 | 293.2445 | 2019-01-02 | 2019-01-23 | 2019-01-11 | 12 | -58 | 6
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1088 | 296 | 832 | 21 | 15.4 | 24 | 323.4 | 2019-01-03 | 2019-01-27 | 2019-01-17 | 10 | -40 | 25
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1088 | 295 | 822 | 19.175 | 15.4 | 24 | 295.295 | 2018-11-24 | 2018-12-18 | 2019-01-17 | -30 | 0 | 25
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1087 | 241 | 835 | 13.5 | 10.4 | 32 | 140.4 | 2018-11-19 | 2018-12-21 | 2019-01-31 | -41 | 0 | 19
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1087 | 289 | 845 | 18.075 | 12.65 | 32 | 228.6488 | 2019-01-02 | 2019-02-03 | 2019-01-23 | 11 | -42 | 21
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 285 | 855 | 13 | 12.6 | 31 | 163.8 | 2019-01-03 | 2019-02-03 | 2019-01-24 | 10 | -41 | 21
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 329 | 835 | 7.416 | 16.884 | 19 | 125.2117 | 2019-01-03 | 2019-01-22 | 2019-01-07 | 15 | -55 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1088 | 328 | 825 | 19.167 | 16.931 | 19 | 324.5165 | 2019-01-03 | 2019-01-22 | 2019-01-07 | 15 | -55 | 6
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 338 | 832 | 6.767 | 14.288 | 16 | 96.6869 | 2019-01-05 | 2019-01-21 | 2019-01-06 | 15 | -57 | 5
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 337 | 822 | 16.086 | 14.292 | 16 | 229.9011 | 2019-01-06 | 2019-01-22 | 2019-01-06 | 16 | -58 | 5
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 310 | 835 | 7.416 | 16.884 | 20 | 125.2117 | 2019-01-07 | 2019-01-27 | 2019-01-10 | 17 | -58 | 6
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 309 | 825 | 19.167 | 16.931 | 20 | 324.5165 | 2019-01-07 | 2019-01-27 | 2019-01-10 | 17 | -58 | 6
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 311 | 621 | 8.95 | 15.97 | 14 | 142.9315 | 2019-01-08 | 2019-01-22 | 2019-01-09 | 13 | -64 | 0
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 312 | 621 | 8.95 | 15.97 | 14 | 142.9315 | 2019-01-08 | 2019-01-22 | 2019-01-09 | 13 | -64 | 0
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 305 | 631 | 10.53 | 15.97 | 13 | 168.1641 | 2019-01-08 | 2019-01-21 | 2019-01-09 | 12 | -64 | 0
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 306 | 631 | 10.53 | 15.97 | 13 | 168.1641 | 2019-01-08 | 2019-01-21 | 2019-01-09 | 12 | -64 | 0
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 335 | 832 | 6.767 | 14.288 | 16 | 96.6869 | 2019-01-08 | 2019-01-24 | 2019-01-07 | 17 | -59 | 5
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 334 | 822 | 16.086 | 14.292 | 16 | 229.9011 | 2019-01-08 | 2019-01-24 | 2019-01-07 | 17 | -59 | 5
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 267 | 283 | 13.7 | 18.32 | 30 | 250.984 | 2019-01-08 | 2019-02-07 | 2019-01-31 | 7 | -57 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 251 | 293 | 22.5 | 18.32 | 30 | 412.2 | 2021-02-08 | 2021-03-10 | 2019-02-01 | 768 | -819 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 252 | 293 | 22.5 | 18.32 | 30 | 412.2 | 2021-02-18 | 2021-03-20 | 2019-02-01 | 778 | -829 | 7
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 246 | 683 | 17.8 | 14.8 | 34 | 263.44 | 2019-01-09 | 2019-02-12 | 2019-02-02 | 10 | -39 | 26
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 247 | 693 | 17.8 | 14.8 | 34 | 263.44 | 2019-01-09 | 2019-02-12 | 2019-02-02 | 10 | -39 | 26
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 255 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2019-01-10 | 2019-02-04 | 2019-01-29 | 6 | -64 | 1
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 256 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2019-01-13 | 2019-02-07 | 2019-01-29 | 9 | -67 | 1
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1087 | 253 | 263 | 16.6 | 18.79 | 25 | 311.914 | 2019-01-13 | 2019-02-07 | 2019-01-29 | 9 | -67 | 1
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1087 | 254 | 263 | 16.6 | 18.79 | 25 | 311.914 | 2019-01-14 | 2019-02-08 | 2019-01-29 | 10 | -68 | 1
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 200 | 801 | 24.3 | 20.03 | 44 | 486.729 | 2021-03-11 | 2021-04-24 | 2019-02-21 | 793 | -855 | 1
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1088 | 248 | 283 | 13.7 | 18.32 | 31 | 250.984 | 2019-01-14 | 2019-02-14 | 2019-02-03 | 11 | -62 | 7
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1087 | 286 | 643 | 19.9 | 14.2 | 26 | 282.58 | 2018-12-03 | 2018-12-29 | 2019-01-24 | -26 | 0 | 27
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 269 | 653 | 17.9 | 14.2 | 26 | 254.18 | 2019-01-17 | 2019-02-12 | 2019-01-25 | 18 | -44 | 27
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1087 | 270 | 803 | 15.5 | 17 | 29 | 263.5 | 2019-01-18 | 2019-02-16 | 2019-01-23 | 24 | -70 | 1
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 257 | 221 | 18 | 15.97 | 11 | 287.46 | 2019-01-18 | 2019-01-29 | 2019-01-23 | 6 | -69 | 1
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 258 | 221 | 19 | 15.97 | 11 | 303.43 | 2019-01-20 | 2019-01-31 | 2019-01-23 | 8 | -71 | 1
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 268 | 803 | 15.5 | 16 | 29 | 248 | 2018-11-10 | 2018-12-09 | 2019-01-24 | -46 | 0 | 1
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 243 | 231 | 14.308 | 15.97 | 14 | 228.4988 | 2019-01-20 | 2019-02-03 | 2019-01-26 | 8 | -68 | 4
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1088 | 244 | 231 | 14.308 | 15.97 | 14 | 228.4988 | 2019-01-20 | 2019-02-03 | 2019-01-26 | 8 | -68 | 4
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1088 | 313 | 102 | 19.76 | 18.47 | 20 | 364.9672 | 2018-11-11 | 2018-12-01 | 2019-01-07 | -37 | 0 | 0
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1088 | 314 | 102 | 19.76 | 18.47 | 20 | 364.9672 | 2019-01-21 | 2019-02-10 | 2019-01-07 | 34 | -71 | 0
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1088 | 227 | 272 | 14.4 | 17.28 | 32 | 248.832 | 2019-01-21 | 2019-02-22 | 2019-02-13 | 9 | -70 | 0
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 228 | 272 | 14.4 | 17.28 | 32 | 248.832 | 2019-01-21 | 2019-02-22 | 2019-02-13 | 9 | -70 | 0
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 225 | 262 | 14.6 | 17.28 | 32 | 252.288 | 2019-01-21 | 2019-02-22 | 2019-02-13 | 9 | -70 | 0
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 226 | 262 | 14.6 | 17.28 | 32 | 252.288 | 2019-01-21 | 2019-02-22 | 2019-02-13 | 9 | -70 | 0
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1088 | 233 | 122 | 15.531 | 12.2 | 17 | 189.4782 | 2019-01-21 | 2019-02-07 | 2019-01-25 | 13 | -61 | 7
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1088 | 234 | 122 | 15.531 | 12.2 | 17 | 189.4782 | 2019-01-22 | 2019-02-08 | 2019-01-25 | 14 | -62 | 7
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 235 | 132 | 18.94 | 12.2 | 17 | 231.068 | 2019-01-22 | 2019-02-08 | 2019-01-25 | 14 | -62 | 7
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 236 | 132 | 18.94 | 12.2 | 17 | 231.068 | 2019-01-22 | 2019-02-08 | 2019-01-25 | 14 | -62 | 7
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 297 | 182 | 18 | 7.3 | 18 | 131.4 | 2019-01-22 | 2019-02-09 | 2019-01-15 | 25 | -63 | 4
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1088 | 298 | 182 | 19 | 7.3 | 18 | 138.7 | 2019-01-22 | 2019-02-09 | 2019-01-15 | 25 | -63 | 4
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 299 | 192 | 13.889 | 7.3 | 18 | 101.3897 | 2019-01-22 | 2019-02-09 | 2019-01-15 | 25 | -63 | 4
42 South-2 | BQM4202A | 18 | 18 | YT | H1087 | 300 | 192 | 13.889 | 7.3 | 18 | 101.3897 | 2019-01-23 | 2019-02-10 | 2019-01-15 | 26 | -64 | 4
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 237 | 103 | 29.101 | 15.68 | 16 | 456.3037 | 2021-03-21 | 2021-04-06 | 2019-01-24 | 803 | -849 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 238 | 103 | 29.101 | 15.68 | 16 | 456.3037 | 2021-04-07 | 2021-04-23 | 2019-01-24 | 820 | -866 | 7
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 205 | 632 | 13.38 | 17.28 | 14 | 231.2064 | 2018-11-21 | 2018-12-05 | 2019-02-03 | -60 | 0 | 4
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 206 | 632 | 13.38 | 17.28 | 14 | 231.2064 | 2019-01-23 | 2019-02-06 | 2019-02-03 | 3 | -63 | 4
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 271 | 623 | 13.38 | 18.79 | 15 | 251.4102 | 2019-01-23 | 2019-02-07 | 2019-01-19 | 19 | -66 | 0
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 272 | 623 | 13.38 | 18.79 | 15 | 251.4102 | 2019-01-23 | 2019-02-07 | 2019-01-19 | 19 | -66 | 0
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 273 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2019-01-23 | 2019-02-07 | 2019-01-19 | 19 | -66 | 0
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1087 | 274 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2019-01-23 | 2019-02-07 | 2019-01-19 | 19 | -66 | 0
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1088 | 215 | 622 | 13.38 | 17.28 | 12 | 231.2064 | 2019-01-23 | 2019-02-04 | 2019-01-30 | 5 | -61 | 5
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 216 | 622 | 13.38 | 17.28 | 12 | 231.2064 | 2019-01-24 | 2019-02-05 | 2019-01-30 | 6 | -62 | 5
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 180 | 111 | 22.2 | 13.8 | 24 | 306.36 | 2021-04-24 | 2021-05-18 | 2019-02-14 | 824 | -881 | 7
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 181 | 111 | 22.2 | 13.8 | 24 | 306.36 | 2021-04-25 | 2021-05-19 | 2019-02-14 | 825 | -882 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 198 | 801 | 28.614 | 19.075 | 34 | 545.812 | 2021-05-19 | 2021-06-22 | 2019-02-19 | 854 | -903 | 9
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 199 | 801 | 28.614 | 19.075 | 34 | 545.812 | 2021-05-20 | 2021-06-23 | 2019-02-19 | 855 | -904 | 9
45 South-4 | BQM4504A | 20 | 21 | ZH | H1087 | 301 | 123 | 16.106 | 12.2 | 23 | 196.4932 | 2019-01-24 | 2019-02-16 | 2019-01-14 | 33 | -64 | 1
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 302 | 123 | 16.106 | 12.2 | 23 | 196.4932 | 2019-01-25 | 2019-02-17 | 2019-01-14 | 34 | -65 | 1
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 303 | 133 | 24.07 | 12.2 | 23 | 293.654 | 2021-06-23 | 2021-07-16 | 2019-01-14 | 914 | -945 | 1
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 304 | 133 | 24.07 | 12.2 | 23 | 293.654 | 2019-04-24 | 2019-05-17 | 2019-01-14 | 123 | -154 | 1
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 275 | 642 | 13.412 | 19.5 | 16 | 261.534 | 2019-01-25 | 2019-02-10 | 2019-01-20 | 21 | -61 | 5
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 276 | 642 | 13.412 | 19.5 | 16 | 261.534 | 2019-01-28 | 2019-02-13 | 2019-01-20 | 24 | -64 | 5
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1088 | 277 | 652 | 13.412 | 19.5 | 16 | 261.534 | 2018-11-25 | 2018-12-11 | 2019-01-20 | -40 | 0 | 5
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 278 | 652 | 13.412 | 19.5 | 16 | 261.534 | 2019-01-28 | 2019-02-13 | 2019-01-20 | 24 | -64 | 5
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 152 | 144 | 17.566 | 15.678 | 24 | 275.3997 | 2019-01-28 | 2019-02-21 | 2019-03-01 | -8 | -62 | 7
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1088 | 153 | 144 | 17.566 | 15.678 | 24 | 275.3997 | 2019-01-28 | 2019-02-21 | 2019-03-01 | -8 | -62 | 7
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 154 | 154 | 19.932 | 15.976 | 24 | 318.4336 | 2019-01-30 | 2019-02-23 | 2019-03-01 | -6 | -64 | 7
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 155 | 154 | 19.932 | 15.976 | 24 | 318.4336 | 2019-01-30 | 2019-02-23 | 2019-03-01 | -6 | -64 | 7
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 219 | 271 | 17.8 | 16 | 32 | 284.8 | 2019-02-01 | 2019-03-05 | 2019-02-13 | 20 | -66 | 6
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 220 | 271 | 17.8 | 16 | 32 | 284.8 | 2019-02-04 | 2019-03-08 | 2019-02-13 | 23 | -69 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1088 | 217 | 261 | 20.1 | 16 | 32 | 321.6 | 2019-02-05 | 2019-03-09 | 2019-02-13 | 24 | -70 | 6
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 218 | 261 | 20.1 | 16 | 32 | 321.6 | 2019-02-06 | 2019-03-10 | 2019-02-13 | 25 | -71 | 6
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1087 | 162 | 124 | 18.618 | 14.354 | 23 | 267.2428 | 2019-02-04 | 2019-02-27 | 2019-02-25 | 2 | -68 | 6
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1088 | 163 | 124 | 18.618 | 14.354 | 23 | 267.2428 | 2019-02-04 | 2019-02-27 | 2019-02-25 | 2 | -68 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 164 | 134 | 22.828 | 14.354 | 23 | 327.6731 | 2021-06-24 | 2021-07-17 | 2019-02-25 | 873 | -939 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 165 | 134 | 22.828 | 14.354 | 23 | 327.6731 | 2021-07-17 | 2021-08-09 | 2019-02-25 | 896 | -962 | 6
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1088 | 260 | 836 | 8 | 21 | 29 | 168 | 2019-02-08 | 2019-03-09 | 2019-01-27 | 41 | -74 | 3
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 259 | 826 | 20.5 | 21 | 29 | 430.5 | 2019-05-14 | 2019-06-12 | 2019-01-27 | 136 | -169 | 3
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 184 | 183 | 8.82 | 15.798 | 21 | 139.3384 | 2019-02-04 | 2019-02-25 | 2019-02-15 | 10 | -69 | 4
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 185 | 183 | 8.82 | 15.798 | 21 | 139.3384 | 2019-02-05 | 2019-02-26 | 2019-02-15 | 11 | -70 | 4
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 186 | 193 | 15.59 | 15.978 | 21 | 249.097 | 2019-02-07 | 2019-02-28 | 2019-02-15 | 13 | -72 | 4
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 187 | 193 | 15.59 | 15.978 | 21 | 249.097 | 2018-11-27 | 2018-12-18 | 2019-02-15 | -59 | 0 | 4
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1088 | 250 | 836 | 8 | 21 | 29 | 168 | 2018-11-27 | 2018-12-26 | 2019-01-28 | -33 | 0 | 3
48 South-10 | BQM4810A | 22 | 21 | MZ | H1088 | 249 | 826 | 20.5 | 21 | 29 | 430.5 | 2019-06-13 | 2019-07-12 | 2019-01-28 | 165 | -198 | 3
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 207 | 143 | 13.809 | 15.686 | 21 | 216.608 | 2019-02-08 | 2019-03-01 | 2019-02-06 | 23 | -69 | 6
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 208 | 143 | 13.809 | 15.686 | 21 | 216.608 | 2019-02-08 | 2019-03-01 | 2019-02-06 | 23 | -69 | 6
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 209 | 153 | 18.919 | 15.5 | 21 | 293.2445 | 2019-02-08 | 2019-03-01 | 2019-02-06 | 23 | -69 | 6
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 210 | 153 | 18.919 | 15.5 | 21 | 293.2445 | 2019-02-08 | 2019-03-01 | 2019-02-06 | 23 | -69 | 6
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 170 | 684 | 14.7 | 20 | 37 | 294 | 2019-02-08 | 2019-03-17 | 2019-03-06 | 11 | -63 | 12
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1087 | 171 | 694 | 14.7 | 20 | 37 | 294 | 2019-02-08 | 2019-03-17 | 2019-03-05 | 12 | -63 | 12
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 290 | 112 | 21 | 8.6 | 17 | 180.6 | 2019-02-08 | 2019-02-25 | 2019-01-12 | 44 | -68 | 5
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 291 | 112 | 21 | 8.6 | 17 | 180.6 | 2019-02-09 | 2019-02-26 | 2019-01-12 | 45 | -69 | 5
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 239 | 292 | 16.6 | 19.5 | 32 | 323.7 | 2019-02-09 | 2019-03-13 | 2019-02-09 | 32 | -66 | 6
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 240 | 292 | 16.6 | 19.5 | 32 | 323.7 | 2019-02-09 | 2019-03-13 | 2019-02-09 | 32 | -66 | 6
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1087 | 322 | 834 | 9.215 | 10.9 | 19 | 100.4435 | 2018-12-04 | 2018-12-23 | 2019-01-13 | -21 | 0 | 4
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 321 | 824 | 15.665 | 11.094 | 19 | 173.7875 | 2019-02-09 | 2019-02-28 | 2019-01-13 | 46 | -67 | 4
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 245 | 282 | 14.7 | 19.5 | 30 | 286.65 | 2019-02-10 | 2019-03-12 | 2019-02-05 | 35 | -65 | 7
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 203 | 621 | 8.95 | 15.97 | 14 | 142.9315 | 2019-02-10 | 2019-02-24 | 2019-02-04 | 20 | -71 | 0
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 204 | 621 | 8.95 | 15.97 | 14 | 142.9315 | 2019-02-10 | 2019-02-24 | 2019-02-04 | 20 | -71 | 0
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 201 | 631 | 10.53 | 15.97 | 13 | 168.1641 | 2019-02-11 | 2019-02-24 | 2019-02-04 | 20 | -72 | 0
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1088 | 202 | 631 | 10.53 | 15.97 | 13 | 168.1641 | 2019-02-11 | 2019-02-24 | 2019-02-04 | 20 | -72 | 0
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 176 | 263 | 16.6 | 18.79 | 24 | 311.914 | 2019-02-11 | 2019-03-07 | 2019-02-21 | 14 | -71 | 1
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1087 | 177 | 263 | 16.6 | 18.79 | 24 | 311.914 | 2019-02-13 | 2019-03-09 | 2019-02-21 | 16 | -73 | 1
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1087 | 316 | 834 | 9.215 | 10.9 | 19 | 100.4435 | 2019-02-13 | 2019-03-04 | 2019-01-14 | 49 | -70 | 4
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1087 | 315 | 824 | 15.665 | 11.094 | 19 | 173.7875 | 2019-02-13 | 2019-03-04 | 2019-01-14 | 49 | -70 | 4
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 242 | 282 | 14.7 | 19.5 | 30 | 286.65 | 2019-02-14 | 2019-03-16 | 2019-02-06 | 38 | -68 | 7
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1087 | 172 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2019-02-14 | 2019-03-11 | 2019-02-24 | 15 | -73 | 1
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1087 | 173 | 273 | 14.5 | 18.79 | 25 | 272.455 | 2019-02-15 | 2019-03-12 | 2019-02-24 | 16 | -74 | 1
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1087 | 139 | 283 | 13.7 | 18.32 | 34 | 250.984 | 2019-02-17 | 2019-03-23 | 2019-03-16 | 7 | -71 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 140 | 293 | 22.5 | 18.32 | 34 | 412.2 | 2021-07-18 | 2021-08-21 | 2019-03-16 | 889 | -953 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 188 | 101 | 30.66 | 9.4 | 32 | 288.204 | 2021-08-10 | 2021-09-11 | 2019-02-19 | 935 | -981 | 0
45 South-4 | BQM4504A | 20 | 21 | ZH | H1087 | 146 | 282 | 14.7 | 19.5 | 33 | 286.65 | 2019-02-17 | 2019-03-22 | 2019-03-15 | 7 | -70 | 6
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1088 | 147 | 292 | 16.6 | 19.5 | 33 | 323.7 | 2019-02-18 | 2019-03-23 | 2019-03-15 | 8 | -71 | 6
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 189 | 231 | 14.308 | 15.97 | 22 | 228.4988 | 2019-02-22 | 2019-03-16 | 2019-02-21 | 23 | -67 | 14
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1088 | 120 | 654 | 19.2 | 15.1 | 37 | 289.92 | 2019-02-22 | 2019-03-31 | 2019-03-26 | 5 | -54 | 27
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 119 | 644 | 22.9 | 15.1 | 37 | 345.79 | 2021-08-22 | 2021-09-28 | 2019-03-26 | 917 | -966 | 27
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1087 | 331 | 833 | 8.709 | 14.287 | 15 | 124.4255 | 2018-12-04 | 2018-12-19 | 2019-01-08 | -20 | 0 | 0
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1088 | 294 | 823 | 16.231 | 14.307 | 18 | 232.2169 | 2019-02-23 | 2019-03-13 | 2019-01-17 | 55 | -81 | 0
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 263 | 653 | 11.2 | 17.72 | 15 | 198.464 | 2019-02-23 | 2019-03-10 | 2019-01-21 | 48 | -78 | 3
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1088 | 264 | 653 | 11.2 | 17.72 | 15 | 198.464 | 2019-02-23 | 2019-03-10 | 2019-01-21 | 48 | -78 | 3
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1088 | 261 | 643 | 13.412 | 17.72 | 15 | 237.6606 | 2019-02-23 | 2019-03-10 | 2019-01-21 | 48 | -78 | 3
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 262 | 643 | 13.412 | 17.72 | 15 | 237.6606 | 2019-02-24 | 2019-03-11 | 2019-01-21 | 49 | -79 | 3
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1088 | 169 | 221 | 17 | 15.97 | 24 | 271.49 | 2018-12-26 | 2019-01-19 | 2019-03-06 | -46 | 0 | 22
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1088 | 323 | 833 | 8.709 | 14.287 | 16 | 124.4255 | 2019-02-24 | 2019-03-12 | 2019-01-11 | 60 | -81 | 0
42 South-2 | BQM4202A | 18 | 18 | YT | H1088 | 293 | 823 | 16.231 | 14.307 | 18 | 232.2169 | 2019-02-25 | 2019-03-15 | 2019-01-18 | 56 | -82 | 0
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 141 | 631 | 10.53 | 15.97 | 11 | 168.1641 | 2019-02-25 | 2019-03-08 | 2019-02-25 | 11 | -48 | 33
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1088 | 211 | 102 | 19.76 | 18.47 | 19 | 364.9672 | 2019-02-25 | 2019-03-16 | 2019-01-31 | 44 | -80 | 0
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 212 | 102 | 19.76 | 18.47 | 19 | 364.9672 | 2019-02-25 | 2019-03-16 | 2019-01-31 | 44 | -80 | 0
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 150 | 272 | 14.4 | 17.28 | 34 | 248.832 | 2019-02-26 | 2019-04-01 | 2019-03-15 | 17 | -80 | 0
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1088 | 151 | 272 | 14.4 | 17.28 | 34 | 248.832 | 2018-12-08 | 2019-01-11 | 2019-03-15 | -63 | 0 | 0
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1088 | 148 | 262 | 14.6 | 17.28 | 34 | 252.288 | 2019-02-26 | 2019-04-01 | 2019-03-15 | 17 | -80 | 0
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1088 | 149 | 262 | 14.6 | 17.28 | 34 | 252.288 | 2019-02-27 | 2019-04-02 | 2019-03-15 | 18 | -81 | 0
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 142 | 621 | 8.95 | 15.97 | 10 | 142.9315 | 2019-01-11 | 2019-01-21 | 2019-02-24 | -34 | 0 | 33
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 161 | 111 | 22.2 | 13.8 | 28 | 306.36 | 2021-09-12 | 2021-10-10 | 2019-02-28 | 955 | -992 | 15
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 182 | 623 | 13.38 | 18.79 | 16 | 251.4102 | 2019-02-27 | 2019-03-15 | 2019-02-14 | 29 | -77 | 0
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 183 | 623 | 13.38 | 18.79 | 16 | 251.4102 | 2019-02-28 | 2019-03-16 | 2019-02-14 | 30 | -78 | 0
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1087 | 145 | 123 | 16.106 | 12.2 | 30 | 196.4932 | 2019-02-28 | 2019-03-30 | 2019-03-09 | 21 | -74 | 4
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 157 | 133 | 24.07 | 12.2 | 30 | 293.654 | 2021-09-29 | 2021-10-29 | 2019-03-05 | 969 | -1018 | 4
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 190 | 182 | 16 | 7.3 | 19 | 116.8 | 2019-03-01 | 2019-03-20 | 2019-02-13 | 35 | -74 | 4
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 191 | 182 | 17 | 7.3 | 19 | 124.1 | 2019-03-01 | 2019-03-20 | 2019-02-13 | 35 | -74 | 4
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1087 | 192 | 192 | 13.889 | 7.3 | 19 | 101.3897 | 2019-03-02 | 2019-03-21 | 2019-02-13 | 36 | -75 | 4
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 193 | 192 | 13.889 | 7.3 | 19 | 101.3897 | 2019-03-02 | 2019-03-21 | 2019-02-13 | 36 | -75 | 4
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 178 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2018-12-14 | 2018-12-29 | 2019-02-14 | -47 | 0 | 0
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1088 | 179 | 633 | 13.38 | 18.79 | 15 | 251.4102 | 2019-03-02 | 2019-03-17 | 2019-02-14 | 31 | -78 | 0
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1087 | 156 | 102 | 19.76 | 18.47 | 43 | 364.9672 | 2019-03-02 | 2019-04-14 | 2019-03-17 | 28 | -77 | 0
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1087 | 194 | 123 | 16.106 | 12.2 | 25 | 196.4932 | 2019-03-05 | 2019-03-30 | 2019-02-13 | 45 | -78 | 1
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 195 | 123 | 16.106 | 12.2 | 25 | 196.4932 | 2019-03-05 | 2019-03-30 | 2019-02-13 | 45 | -78 | 1
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 196 | 133 | 24.07 | 12.2 | 25 | 293.654 | 2019-05-18 | 2019-06-12 | 2019-02-13 | 119 | -152 | 1
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 197 | 133 | 24.07 | 12.2 | 25 | 293.654 | 2021-10-11 | 2021-11-05 | 2019-02-13 | 996 | -1029 | 1
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1088 | 135 | 271 | 17.8 | 16 | 36 | 284.8 | 2019-03-06 | 2019-04-11 | 2019-03-18 | 24 | -74 | 6
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1088 | 136 | 271 | 17.8 | 16 | 36 | 284.8 | 2019-03-08 | 2019-04-13 | 2019-03-18 | 26 | -76 | 6
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1088 | 133 | 261 | 20.1 | 16 | 36 | 321.6 | 2018-12-22 | 2019-01-27 | 2019-03-18 | -50 | 0 | 6
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1088 | 134 | 261 | 20.1 | 16 | 36 | 321.6 | 2019-03-09 | 2019-04-14 | 2019-03-18 | 27 | -77 | 6
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1088 | 166 | 122 | 15.531 | 12.2 | 31 | 189.4782 | 2019-03-09 | 2019-04-09 | 2019-03-07 | 33 | -81 | -1
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 167 | 132 | 18.94 | 12.2 | 31 | 231.068 | 2019-03-10 | 2019-04-10 | 2019-03-07 | 34 | -82 | -1
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1088 | 132 | 273 | 14.5 | 18.79 | 31 | 272.455 | 2019-03-10 | 2019-04-10 | 2019-03-17 | 24 | -74 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1088 | 131 | 263 | 16.6 | 18.79 | 31 | 311.914 | 2019-03-10 | 2019-04-10 | 2019-03-18 | 23 | -74 | 6
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1087 | 158 | 632 | 13.38 | 17.28 | 19 | 231.2064 | 2019-03-11 | 2019-03-30 | 2019-02-28 | 30 | -69 | 12
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1088 | 117 | 124 | 18.618 | 14.354 | 39 | 267.2428 | 2019-03-11 | 2019-04-19 | 2019-04-01 | 18 | -70 | 10
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 118 | 134 | 22.828 | 14.354 | 39 | 327.6731 | 2021-10-30 | 2021-12-08 | 2019-04-01 | 982 | -1034 | 10
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 129 | 143 | 13.809 | 15.686 | 37 | 216.608 | 2019-03-11 | 2019-04-17 | 2019-03-25 | 23 | -72 | 7
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 130 | 153 | 18.919 | 15.5 | 37 | 293.2445 | 2019-03-11 | 2019-04-17 | 2019-03-25 | 23 | -72 | 7
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1088 | 168 | 112 | 21 | 8.6 | 21 | 180.6 | 2019-03-12 | 2019-04-02 | 2019-02-20 | 41 | -74 | 5
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1087 | 159 | 622 | 13.38 | 17.28 | 17 | 231.2064 | 2019-03-12 | 2019-03-29 | 2019-02-26 | 31 | -67 | 12
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1087 | 174 | 112 | 21 | 8.6 | 21 | 180.6 | 2019-03-13 | 2019-04-03 | 2019-02-16 | 46 | -74 | 5
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1087 | 175 | 112 | 21 | 8.6 | 21 | 180.6 | 2019-03-13 | 2019-04-03 | 2019-02-16 | 46 | -74 | 5
No.10 North-22 | PPT1061A | 20 | 20 | yard HN | H1087 | 107 | 271 | 17.8 | 16 | 37 | 284.8 | 2019-03-13 | 2019-04-19 | 2019-04-06 | 13 | -73 | 6
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1088 | 106 | 261 | 20.1 | 16 | 37 | 321.6 | 2018-12-30 | 2019-02-05 | 2019-04-06 | -60 | 0 | 6
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 143 | 182 | 15 | 7.3 | 21 | 109.5 | 2019-03-14 | 2019-04-04 | 2019-03-07 | 28 | -73 | 6
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 144 | 192 | 13.889 | 7.3 | 21 | 101.3897 | 2019-03-14 | 2019-04-04 | 2019-03-07 | 28 | -73 | 6
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 114 | 144 | 17.566 | 15.678 | 36 | 275.3997 | 2019-03-14 | 2019-04-19 | 2019-03-31 | 19 | -69 | 8
No.0 East-12 | PPT0056A | 20 | 21 | QS | H1088 | 99 | 154 | 19.932 | 15.976 | 45 | 318.4336 | 2019-03-16 | 2019-04-30 | 2019-04-18 | 12 | -71 | 8
42 South-2 | BQM4202A | 18 | 18 | YT | H1087 | 123 | 835 | 7.416 | 16.884 | 23 | 125.2117 | 2019-03-16 | 2019-04-08 | 2019-03-12 | 27 | -71 | 6
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 124 | 835 | 7.416 | 16.884 | 23 | 125.2117 | 2019-01-04 | 2019-01-27 | 2019-03-12 | -44 | 0 | 6
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1088 | 121 | 825 | 19.167 | 16.931 | 23 | 324.5165 | 2019-03-17 | 2019-04-09 | 2019-03-12 | 28 | -72 | 6
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 122 | 825 | 19.167 | 16.931 | 23 | 324.5165 | 2019-03-17 | 2019-04-09 | 2019-03-12 | 28 | -72 | 6
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 160 | 103 | 29.101 | 15.68 | 30 | 456.3037 | 2019-06-13 | 2019-07-13 | 2019-03-09 | 126 | -160 | 5
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 35 | 801 | 28.614 | 19.075 | 65 | 545.812 | 2021-11-06 | 2022-01-10 | 2019-05-31 | 955 | -1036 | 2
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1087 | 127 | 832 | 6.767 | 14.288 | 20 | 96.6869 | 2019-03-17 | 2019-04-06 | 2019-03-15 | 22 | -68 | 5
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1087 | 128 | 832 | 6.767 | 14.288 | 20 | 96.6869 | 2019-03-17 | 2019-04-06 | 2019-03-15 | 22 | -68 | 5
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1087 | 125 | 822 | 16.086 | 14.292 | 20 | 229.9011 | 2019-03-17 | 2019-04-06 | 2019-03-15 | 22 | -68 | 5
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 126 | 822 | 16.086 | 14.292 | 20 | 229.9011 | 2019-03-18 | 2019-04-07 | 2019-03-15 | 23 | -69 | 5
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 137 | 623 | 13.38 | 18.79 | 19 | 251.4102 | 2019-03-18 | 2019-04-06 | 2019-03-06 | 31 | -69 | 3
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1088 | 138 | 633 | 13.38 | 18.79 | 19 | 251.4102 | 2019-03-18 | 2019-04-06 | 2019-03-06 | 31 | -69 | 3
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 82 | 293 | 22.5 | 18.32 | 36 | 412.2 | 2021-12-09 | 2022-01-14 | 2019-04-15 | 1005 | -1062 | 7
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 83 | 293 | 22.5 | 18.32 | 36 | 412.2 | 2022-01-11 | 2022-02-16 | 2019-04-15 | 1038 | -1095 | 7
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1088 | 84 | 283 | 13.7 | 18.32 | 36 | 250.984 | 2019-01-13 | 2019-02-18 | 2019-04-15 | -56 | 0 | 7
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1087 | 85 | 283 | 13.7 | 18.32 | 36 | 250.984 | 2019-01-13 | 2019-02-18 | 2019-04-15 | -56 | 0 | 7
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1087 | 90 | 803 | 15.5 | 14 | 35 | 217 | 2019-01-08 | 2019-02-12 | 2019-04-05 | -52 | 0 | 1
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 91 | 803 | 15.5 | 15 | 35 | 232.5 | 2019-01-08 | 2019-02-12 | 2019-04-05 | -52 | 0 | 1
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1088 | 115 | 183 | 8.82 | 15.798 | 27 | 139.3384 | 2019-01-14 | 2019-02-10 | 2019-03-23 | -41 | 0 | 6
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 94 | 272 | 14.4 | 17.28 | 39 | 248.832 | 2019-01-14 | 2019-02-22 | 2019-04-17 | -54 | 0 | 6
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1088 | 116 | 193 | 15.59 | 15.978 | 27 | 249.097 | 2019-03-21 | 2019-04-17 | 2019-03-23 | 25 | -66 | 6
No.10 North-6 | PPT1053A | 20 | 20 | yard ZH | H1087 | 93 | 262 | 14.6 | 17.28 | 39 | 252.288 | 2019-03-21 | 2019-04-29 | 2019-04-17 | 12 | -66 | 6
48 North-3 | BQM4853A | 36 | 21 | HN | H1088 | 80 | 101 | 30.66 | 9.4 | 38 | 288.204 | 2019-07-14 | 2019-08-21 | 2019-04-15 | 128 | -180 | 0
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1088 | 102 | 642 | 13.412 | 19.5 | 20 | 261.534 | 2019-03-22 | 2019-04-11 | 2019-03-26 | 16 | -60 | 5
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1088 | 103 | 642 | 13.412 | 19.5 | 20 | 261.534 | 2019-03-22 | 2019-04-11 | 2019-03-26 | 16 | -60 | 5
45 South-4 | BQM4504A | 20 | 21 | ZH | H1088 | 104 | 652 | 13.412 | 19.5 | 20 | 261.534 | 2019-03-23 | 2019-04-12 | 2019-03-26 | 17 | -61 | 5
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1088 | 105 | 652 | 13.412 | 19.5 | 20 | 261.534 | 2019-03-24 | 2019-04-13 | 2019-03-26 | 18 | -62 | 5
No.8 North-18 | PPT0859A | 20 | 22 | HL | H1087 | 33 | 283 | 13.7 | 18.32 | 39 | 250.984 | 2019-03-24 | 2019-05-02 | 2019-05-10 | -8 | -61 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1087 | 34 | 293 | 22.5 | 18.32 | 39 | 412.2 | 2022-01-15 | 2022-02-23 | 2019-05-10 | 1020 | -1089 | 6
48 South-3 | BQM4803A | 36 | 21 | MZ | H1087 | 7 | 801 | 28.614 | 19.075 | 67 | 545.812 | 2022-02-17 | 2022-04-25 | 2019-06-20 | 1040 | -1123 | 2
No.10 North-14 | PPT1057A | 20 | 20 | RH | H1088 | 40 | 282 | 14.7 | 19.5 | 36 | 286.65 | 2019-03-30 | 2019-05-05 | 2019-05-07 | -2 | -64 | 6
No.0 East-16 | PPT0058A | 18 | 21 | QS | H1088 | 41 | 292 | 16.6 | 19.5 | 36 | 323.7 | 2019-03-31 | 2019-05-06 | 2019-05-07 | -1 | -65 | 6
No.10 North-20 | PPT1060A | 20 | 20 | yard HN | H1088 | 81 | 231 | 14.308 | 15.97 | 24 | 228.4988 | 2019-03-31 | 2019-04-24 | 2019-04-13 | 11 | -57 | 14
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1087 | 58 | 221 | 16 | 15.97 | 25 | 255.52 | 2019-02-12 | 2019-03-09 | 2019-04-25 | -47 | 0 | 22
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 88 | 836 | 8 | 21 | 35 | 168 | 2019-01-25 | 2019-03-01 | 2019-04-09 | -39 | 0 | 3
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1087 | 89 | 836 | 8 | 21 | 35 | 168 | 2019-01-28 | 2019-03-04 | 2019-04-09 | -36 | -3 | 3
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 86 | 826 | 20.5 | 21 | 35 | 430.5 | 2019-07-13 | 2019-08-17 | 2019-04-09 | 130 | -169 | 3
48 South-10 | BQM4810A | 22 | 21 | MZ | H1087 | 87 | 826 | 20.5 | 21 | 35 | 430.5 | 2019-08-18 | 2019-09-22 | 2019-04-09 | 166 | -205 | 3
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 36 | 801 | 28.614 | 19.075 | 39 | 545.812 | 2022-02-24 | 2022-04-04 | 2019-05-05 | 1065 | -1119 | 9
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 37 | 801 | 28.614 | 19.075 | 39 | 545.812 | 2022-04-05 | 2022-05-14 | 2019-05-05 | 1105 | -1159 | 9
No.8 South-13 | PPT0807A | 20 | 22 | XZY | H1088 | 49 | 123 | 16.106 | 12.2 | 34 | 196.4932 | 2019-03-31 | 2019-05-04 | 2019-04-29 | 5 | -62 | 4
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 54 | 133 | 24.07 | 12.2 | 34 | 293.654 | 2019-08-22 | 2019-09-25 | 2019-04-25 | 153 | -206 | 4
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 38 | 631 | 10.53 | 15.97 | 11 | 168.1641 | 2019-03-31 | 2019-04-11 | 2019-04-15 | -4 | -33 | 33
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 57 | 111 | 22.2 | 13.8 | 29 | 306.36 | 2019-09-26 | 2019-10-25 | 2019-04-17 | 191 | -229 | 15
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1087 | 64 | 836 | 8 | 21 | 34 | 168 | 2019-02-06 | 2019-03-12 | 2019-04-18 | -37 | -3 | 8
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1087 | 63 | 826 | 20 | 21 | 34 | 420 | 2019-02-11 | 2019-03-17 | 2019-04-18 | -32 | -8 | 8
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1088 | 79 | 803 | 15.5 | 13 | 35 | 201.5 | 2019-01-28 | 2019-03-04 | 2019-04-12 | -39 | 0 | 1
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 67 | 834 | 9.215 | 10.9 | 22 | 100.4435 | 2019-02-02 | 2019-02-24 | 2019-04-14 | -49 | 0 | 6
No.8 South-5 | PPT0803A | 20 | 22 | HY | H1087 | 66 | 824 | 15.665 | 11.094 | 22 | 173.7875 | 2019-04-01 | 2019-04-23 | 2019-04-14 | 9 | -58 | 6
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 39 | 621 | 8.95 | 15.97 | 10 | 142.9315 | 2019-04-02 | 2019-04-12 | 2019-04-14 | -2 | -32 | 33
No.8 North-28 | PPT0864A | 20 | 22 | flexible | H1087 | 70 | 832 | 6.767 | 14.288 | 21 | 96.6869 | 2019-04-02 | 2019-04-23 | 2019-04-13 | 10 | -58 | 6
No.10 South-25 | PPT1013A | 18 | 20 | yard HN | H1087 | 71 | 833 | 8.709 | 14.287 | 21 | 124.4255 | 2019-04-03 | 2019-04-24 | 2019-04-13 | 11 | -59 | 6
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1087 | 68 | 822 | 16.086 | 14.292 | 21 | 229.9011 | 2019-02-13 | 2019-03-06 | 2019-04-13 | -38 | -10 | 6
No.0 East-14 | PPT0057A | 20 | 21 | QS | H1087 | 69 | 823 | 16.231 | 14.307 | 21 | 232.2169 | 2019-04-03 | 2019-04-24 | 2019-04-13 | 11 | -59 | 6
No.0 West-1 | PPT0001A | 20 | 21 | MZ | H1088 | 50 | 102 | 19.76 | 18.47 | 47 | 364.9672 | 2019-04-04 | 2019-05-21 | 2019-05-09 | 12 | -65 | 0
No.8 South-3 | PPT0802A | 20 | 22 | HY | H1087 | 97 | 653 | 11.2 | 17.72 | 19 | 198.464 | 2019-04-04 | 2019-04-23 | 2019-03-29 | 25 | -59 | 3
No.0 East-18 | PPT0059A | 18 | 21 | QS | H1087 | 98 | 653 | 11.2 | 17.72 | 19 | 198.464 | 2019-04-05 | 2019-04-24 | 2019-03-29 | 26 | -60 | 3
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 95 | 643 | 13.412 | 17.72 | 19 | 237.6606 | 2019-02-13 | 2019-03-04 | 2019-03-29 | -25 | -9 | 3
No.10 South-1 | PPT1001A | 20 | 20 | yard ZH | H1087 | 96 | 643 | 13.412 | 17.72 | 19 | 237.6606 | 2019-04-05 | 2019-04-24 | 2019-03-29 | 26 | -60 | 3
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1087 | 59 | 122 | 15.531 | 12.2 | 31 | 189.4782 | 2019-02-19 | 2019-03-22 | 2019-04-22 | -31 | -17 | -1
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1087 | 60 | 132 | 18.94 | 12.2 | 31 | 231.068 | 2019-02-19 | 2019-03-22 | 2019-04-22 | -31 | -17 | -1
No.0 East-6 | PPT0053A | 20 | 21 | MZ | H1088 | 73 | 292 | 16.6 | 19.5 | 36 | 323.7 | 2019-04-07 | 2019-05-13 | 2019-04-24 | 19 | -57 | 6
No.8 South-1 | PPT0801A | 20 | 22 | HY | H1088 | 74 | 292 | 16.6 | 19.5 | 36 | 323.7 | 2019-04-07 | 2019-05-13 | 2019-04-24 | 19 | -57 | 6
No.8 South-15 | PPT0808A | 20 | 22 | HL | H1088 | 45 | 273 | 14.5 | 18.79 | 30 | 272.455 | 2019-04-07 | 2019-05-07 | 2019-04-30 | 7 | -56 | 6
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1088 | 42 | 263 | 16.6 | 18.79 | 30 | 311.914 | 2019-02-23 | 2019-03-25 | 2019-05-01 | -37 | -13 | 6
No.8 South-19 | PPT0810A | 20 | 22 | HL | H1088 | 77 | 282 | 14.7 | 19.5 | 35 | 286.65 | 2019-04-07 | 2019-05-12 | 2019-04-22 | 20 | -55 | 7
No.8 North-26 | PPT0863A | 20 | 22 | flexible | H1088 | 78 | 282 | 14.7 | 19.5 | 35 | 286.65 | 2019-04-07 | 2019-05-12 | 2019-04-22 | 20 | -55 | 7
No.10 South-5 | PPT1003A | 20 | 20 | yard ZH | H1087 | 110 | 834 | 9.215 | 10.9 | 22 | 100.4435 | 2019-04-08 | 2019-04-30 | 2019-03-27 | 34 | -58 | 4
42 South-2 | BQM4202A | 18 | 18 | YT | H1087 | 111 | 834 | 9.215 | 10.9 | 22 | 100.4435 | 2019-04-09 | 2019-05-01 | 2019-03-27 | 35 | -59 | 4
No.10 South-13 | PPT1007A | 18 | 20 | RH | H1087 | 108 | 824 | 15.665 | 11.094 | 22 | 173.7875 | 2019-04-10 | 2019-05-02 | 2019-03-27 | 36 | -60 | 4
No.10 South-15 | PPT1008A | 18 | 20 | yard HN | H1087 | 109 | 824 | 15.665 | 11.094 | 22 | 173.7875 | 2019-04-10 | 2019-05-02 | 2019-03-27 | 36 | -60 | 4
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 22 | 143 | 13.809 | 15.686 | 39 | 216.608 | 2019-02-25 | 2019-04-05 | 2019-05-13 | -38 | -13 | 7
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 23 | 153 | 18.919 | 15.5 | 39 | 293.2445 | 2019-03-02 | 2019-04-10 | 2019-05-13 | -33 | -18 | 7
No.0 East-2 | PPT0051A | 20 | 21 | MZ | H1088 | 72 | 112 | 21 | 8.6 | 21 | 180.6 | 2019-04-11 | 2019-05-02 | 2019-04-06 | 26 | -59 | 5
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1087 | 62 | 653 | 11.2 | 17.72 | 19 | 198.464 | 2019-03-05 | 2019-03-24 | 2019-04-12 | -19 | -21 | 6
No.10 South-23 | PPT1012A | 18 | 20 | yard HN | H1088 | 76 | 643 | 13.412 | 17.72 | 19 | 237.6606 | 2019-04-10 | 2019-04-29 | 2019-04-09 | 20 | -57 | 6
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 61 | 652 | 13.412 | 19.5 | 19 | 261.534 | 2019-03-05 | 2019-03-24 | 2019-04-12 | -19 | -21 | 6
No.10 North-8 | PPT1054A | 20 | 20 | yard ZH | H1088 | 75 | 642 | 13.412 | 19.5 | 19 | 261.534 | 2019-04-11 | 2019-04-30 | 2019-04-09 | 21 | -58 | 6
No.8 South-21 | PPT0811A | 20 | 22 | HL | H1087 | 13 | 124 | 18.618 | 14.354 | 37 | 267.2428 | 2019-04-11 | 2019-05-18 | 2019-05-14 | 4 | -54 | 10
48 North-3 | BQM4853A | 36 | 21 | HN | H1087 | 14 | 134 | 22.828 | 14.354 | 37 | 327.6731 | 2019-10-26 | 2019-12-02 | 2019-05-14 | 202 | -252 | 10
No.10 South-19 | PPT1010A | 18 | 20 | yard HN | H1088 | 51 | 632 | 13.38 | 17.28 | 19 | 231.2064 | 2019-04-12 | 2019-05-01 | 2019-04-18 | 13 | -52 | 12
No.10 South-21 | PPT1011A | 18 | 20 | yard HN | H1087 | 112 | 833 | 8.709 | 14.287 | 17 | 124.4255 | 2019-04-12 | 2019-04-29 | 2019-03-20 | 40 | -62 | 0
No.10 South-3 | PPT1002A | 20 | 20 | yard ZH | H1087 | 113 | 833 | 8.709 | 14.287 | 17 | 124.4255 | 2019-04-12 | 2019-04-29 | 2019-03-20 | 40 | -62 | 0
No.8 South-17 | PPT0809A | 20 | 22 | HL | H1088 | 100 | 823 | 16.231 | 14.307 | 21 | 232.2169 | 2019-04-12 | 2019-05-03 | 2019-03-31 | 33 | -62 | 0
No.10 North-24 | PPT1062A | 20 | 20 | yard HN | H1088 | 101 | 823 | 16.231 | 14.307 | 21 | 232.2169 | 2019-04-13 | 2019-05-04 | 2019-03-31 | 34 | -63 | 0
48 South-3 | BQM4803A | 36 | 21 | MZ | H1088 | 46 | 182 | 25 | 7.3 | 21 | 182.5 | 2022-04-26 | 2022-05-17 | 2019-04-23 | 1120 | -1165 | 6
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1088 | 47 | 192 | 13.889 | 7.3 | 21 | 101.3897 | 2019-03-05 | 2019-03-26 | 2019-04-23 | -28 | -17 | 6
45 South-4 | BQM4504A | 20 | 21 | ZH | H1087 | 12 | 144 | 17.566 | 15.678 | 36 | 275.3997 | 2019-04-13 | 2019-05-19 | 2019-05-15 | 4 | -54 | 8
No.10 North-12 | PPT1056A | 20 | 20 | RH | H1087 | 4 | 154 | 19.932 | 15.976 | 47 | 318.4336 | 2019-04-14 | 2019-05-31 | 2019-06-06 | -6 | -55 | 8
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1088 | 52 | 622 | 13.38 | 17.28 | 17 | 231.2064 | 2019-03-07 | 2019-03-24 | 2019-04-16 | -23 | -13 | 12
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1088 | 48 | 803 | 15.5 | 12 | 35 | 186 | 2019-03-10 | 2019-04-14 | 2019-04-27 | -13 | -26 | 1
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1087 | 25 | 834 | 9.215 | 10.9 | 22 | 100.4435 | 2019-03-13 | 2019-04-04 | 2019-04-29 | -25 | -24 | 6
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1087 | 24 | 824 | 15.665 | 11.094 | 22 | 173.7875 | 2019-03-18 | 2019-04-09 | 2019-04-29 | -20 | -29 | 6
No.10 South-9 | PPT1005A | 20 | 20 | RH | H1087 | 6 | 271 | 17.8 | 16 | 37 | 284.8 | 2019-03-23 | 2019-04-29 | 2019-05-25 | -26 | -34 | 6
No.0 West-5 | PPT0003A | 20 | 21 | MZ | H1087 | 5 | 261 | 20.1 | 16 | 37 | 321.6 | 2019-03-25 | 2019-05-01 | 2019-05-25 | -24 | -36 | 6
No.8 North-22 | PPT0861A | 20 | 22 | HY | H1087 | 29 | 832 | 6.767 | 14.288 | 21 | 96.6869 | 2019-04-14 | 2019-05-05 | 2019-04-28 | 7 | -55 | 6
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1087 | 30 | 833 | 8.709 | 14.287 | 21 | 124.4255 | 2019-03-23 | 2019-04-13 | 2019-04-28 | -15 | -33 | 6
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1087 | 26 | 822 | 16.086 | 14.292 | 21 | 229.9011 | 2019-03-25 | 2019-04-15 | 2019-04-28 | -13 | -35 | 6
No.10 North-16 | PPT1058A | 20 | 20 | yard HN | H1087 | 27 | 823 | 16.231 | 14.307 | 21 | 232.2169 | 2019-03-25 | 2019-04-15 | 2019-04-28 | -13 | -35 | 6
45 South-3 | BQM4503A | 33 | 21 | ZH | H1088 | 53 | 103 | 29.101 | 15.68 | 32 | 456.3037 | 2022-05-15 | 2022-06-16 | 2019-04-28 | 1145 | -1181 | 5
No.8 North-14 | PPT0857A | 20 | 22 | HL | H1087 | 19 | 836 | 8 | 21 | 34 | 168 | 2019-03-26 | 2019-04-29 | 2019-05-08 | -9 | -31 | 8
No.0 East-10 | PPT0055A | 20 | 21 | MZ | H1087 | 18 | 826 | 20 | 21 | 34 | 420 | 2019-03-27 | 2019-04-30 | 2019-05-08 | -8 | -32 | 8
No.0 West-7 | PPT0004A | 20 | 21 | MZ | H1087 | 56 | 835 | 7.416 | 16.884 | 27 | 125.2117 | 2019-04-05 | 2019-05-02 | 2019-04-19 | 13 | -47 | 0
No.10 North-2 | PPT1051A | 20 | 20 | yard ZH | H1087 | 55 | 825 | 19.167 | 16.931 | 27 | 324.5165 | 2019-04-06 | 2019-05-03 | 2019-04-19 | 14 | -48 | 0
No.0 East-8 | PPT0054A | 20 | 21 | MZ | H1088 | 43 | 623 | 13.38 | 18.79 | 19 | 251.4102 | 2019-04-10 | 2019-04-29 | 2019-04-22 | 7 | -45 | 3
No.10 North-10 | PPT1055A | 20 | 20 | RH | H1088 | 44 | 633 | 13.38 | 18.79 | 19 | 251.4102 | 2019-04-15 | 2019-05-04 | 2019-04-22 | 12 | -50 | 3
No.0 West-3 | PPT0002A | 20 | 21 | MZ | H1087 | 10 | 183 | 8.82 | 15.798 | 27 | 139.3384 | 2019-04-15 | 2019-05-12 | 2019-05-09 | 3 | -44 | 6
No.8 North-16 | PPT0858A | 20 | 22 | HL | H1087 | 21 | 653 | 11.2 | 17.72 | 17 | 198.464 | 2019-04-11 | 2019-04-28 | 2019-04-26 | 2 | -40 | 6
No.10 South-17 | PPT1009A | 18 | 20 | yard HN | H1087 | 32 | 643 | 13.412 | 17.72 | 17 | 237.6606 | 2019-04-18 | 2019-05-05 | 2019-04-23 | 12 | -47 | 6
No.0 East-4 | PPT0052A | 20 | 21 | MZ | H1087 | 11 | 193 | 15.59 | 15.978 | 27 | 249.097 | 2019-04-18 | 2019-05-15 | 2019-05-09 | 6 | -47 | 6
No.10 North-18 | PPT1059A | 20 | 20 | yard HN | H1087 | 20 | 652 | 13.412 | 19.5 | 17 | 261.534 | 2019-04-14 | 2019-05-01 | 2019-04-26 | 5 | -43 | 6
No.10 North-4 | PPT1052A | 20 | 20 | yard ZH | H1087 | 31 | 642 | 13.412 | 19.5 | 17 | 261.534 | 2019-04-15 | 2019-05-02 | 2019-04-23 | 9 | -44 | 6
No.10 South-11 | PPT1006A | 20 | 20 | RH | H1087 | 2 | 272 | 14.4 | 17.28 | 39 | 248.832 | 2019-04-16 | 2019-05-25 | 2019-06-05 | -11 | -43 | 6
No.8 South-7 | PPT0804A | 20 | 22 | XZY | H1087 | 1 | 262 | 14.6 | 17.28 | 39 | 252.288 | 2019-04-18 | 2019-05-27 | 2019-06-05 | -9 | -45 | 6
No.0 East-20 | PPT0060A | 18 | 21 | QS | H1087 | 9 | 835 | 7.416 | 16.884 | 27 | 125.2117 | 2019-04-20 | 2019-05-17 | 2019-05-09 | 8 | -42 | 0
No.10 South-7 | PPT1004A | 20 | 20 | yard ZH | H1087 | 8 | 825 | 19.167 | 16.931 | 27 | 324.5165 | 2019-04-20 | 2019-05-17 | 2019-05-09 | 8 | -42 | 0